## JJOC
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Establish Standard Procedures for Measuring Outcomes
Strategy #1: Identify Outcomes measures | [5 empty] | 0%
1.1.1 | Establish outcomes measures for statewide system improvement measures | JJOC | 2017-12-15 | 2018-06-30 |  | 0%
Goal #2 - Reporting Requirements of JJOC and DCFS
Strategy #1: Annual LCB Compliance Report | [5 empty] | 0%
2.1.1 | Create a template | JJOC | 2017-12-15 |  |  | 0%
2.1.2 | Establish ownership of this report | JJOC |  |  |  | 0%
2.1.3 | Submit completed report | JJOC |  | 2018-01-01 |  | 0%
Strategy #2: Annual Report to the Governor | [5 empty] | 0%
2.2.1 | Create a template | JJOC |  |  |  | 0%
2.2.2 | Establish ownership of this report | JJOC |  |  |  | 0%
2.2.3 | Submit completed report | JJOC |  | 2019-07-01 |  | 0%
Goal #3 - Annual Quality Assurance Review
Strategy #1: Quality Assurance Tool | [5 empty] | 0%
3.1.1 | JJOC must select QA Tool | JJOC |  |  |  | 0%
3.1.2 | JJOC to receive training on use of tool | JJOC |  |  |  | 0%
3.1.3 | Determine who will be responsible for conducting review | JJOC |  |  |  | 0%
Strategy #2: Utilization of Tool and Review Process | [5 empty] | 0%
3.2.1 | Determine timeline of each facility review | DCFS QA Contractor |  |  |  | 0%
3.2.2 | Develop procedures for use of QA Review Tool | DCFS QA Contractor |  |  |  | 0%
3.2.3 | Develop procedures for Quality Improvement Plan | DCFS QA Contractor |  |  |  | 0%
3.2.4 | Develop procedures for JJOC to review QA Reviews from facilities | DCFS QA Contractor |  |  |  | 0%
Goal #4 - Adoption and Implementation of New Regulations
Strategy #1: Ability to withhold funding for non-compliance of EB Standards | [5 empty] | 0%
4.1.1 | Identify appropriate placement for this/policy or regulation | JJOC |  |  |  | 0%
4.1.2 | Draft language for policy or regulation | JJOC |  |  |  | 0%
Strategy #2: Review and Revise NRS 62H | [5 empty] | 0%
4.2.1 | Review for appropriate language | JJOC |  |  |  | 0%
4.2.2 | Review for appropriate crimes | JJOC |  |  |  | 0%
4.2.3 | Review for reporting requirements | JJOC |  |  |  | 0%
4.2.4 | Add language for reporting requirements | JJOC |  |  |  | 0%
4.2.5 | Draft updated version for review by JJOC | JJOC |  |  |  | 0%
4.2.6 | Determine process for adopting new regulation | JJOC |  |  |  | 0%
Strategy #3: Review and Revise NAC 62H | [5 empty] | 0%
4.3.1 | Review for appropriate language | JJOC |  |  |  | 0%
4.3.2 | Review for appropriate crimes | JJOC |  |  |  | 0%
4.3.3 | Review for reporting requirements | JJOC |  |  |  | 0%
4.3.4 | Add language for reporting requirements | JJOC |  |  |  | 0%
4.3.5 | Draft updated version for review by JJOC | JJOC |  |  |  | 0%
4.3.6 | Determine process for adopting new regulation | JJOC |  |  |  | 0%
Goal #5 - Development of By-Laws and Participation Requirements | [5 empty] | 0%
5.1 | Develop By-Laws for JJOC | JJOC |  |  |  | 0%
5.2 | Determine participation requirements | JJOC |  |  |  | 0%
5.3 | Review By-Laws | JJOC |  |  |  | 0%
5.4 | Approve By-Laws | JJOC |  |  |  | 0%
Goal #6: Policy Development (Cross Reference DCFS Tab)
Strategy #1: Family Engagement Plan
0%
0%
Strategy #2: Court Findings Prior to Commitment
0%
0%
Strategy #3: Individual Case Plan
0%
0%
Strategy #4: Placement of Child
0%
0%
Strategy #5: Out of State (OOS) Placement of Child
0%
0%
Strategy #6: Release of Information/Information Sharing
0%
0%
Strategy #7: System Information Requirements (Data Collection Activities)
0%
Deliverable #1: Policy Development and Adoption
1.1 | Family Engagement Plan | JJOC task or JJOC assigns to ?
1.2 | Court Findings Prior to Commitment | JJOC task or JJOC assigns to ?
1.3 | Individual Case Plan | JJOC task or JJOC assigns to ?
1.4 | Placement of Child | JJOC task or JJOC assigns to ?
1.5 | Out of State (OOS) Placement of Child | JJOC task or JJOC assigns to ?
1.6 | Release of Information/Information Sharing | JJOC task or JJOC assigns to ?
1.7 | System Information Requirements (Data Collection Activities) | JJOC task or JJOC assigns to ?
Deliverable #2: Outcome Measures
2.1 | Establish outcomes measures for statewide system improvement measures
Deliverable #3: Commission By Laws
3.1 | Completed and adopted by laws
Deliverable #4: Annual Report
Deliverable #5: Regulations
Recidivism
NRS 62 H
NAC 62 H
Strategic Plan
Performance Measures
Evidence Based Standards

## Strategic Plan
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Evidence Based Practices
Strategy #1: Vendor Procurement for Resource Center | [5 empty] | 70%
1.1.1 | Develop RFP to select a vendor for EBP Resource Center | DCFS | 2017-09-28 | 2017-11-16 | 2017-11-16 | 100% |  | Selection Made | 3 vendor applications received
1.1.2 | Evaluation and selection of Vendor | State Purchasing | 2017-11-16 | 2017-11-16 | 2017-11-16 | 100% |  | Selection Made | Evaluation committee of 4; selection made
1.1.3 | Contract development | State Purchasing | 2017-11-16 | 2017-12-15 |  | 100% |  |  | Routing contract for signatures
1.1.4 | BOE Review of Contract | State Purchasing | 2017-11-16 | 2017-02-13 |  | 50%
1.1.5 | Establish Invoice Process | Brian Dahlberg | 2018-01-12 | 2018-02-13 |  | 0%
Strategy #2: Selection of EBP Models by Vendor | [5 empty] | 0%
1.2.1 | Vendor to identify appropriate EBP's for state-wide utilization | Vendor | 2017-01-12 |  |  | 0%
1.2.2 | Determine uniform standards that EBP must follow | Sub committee | 2017-01-12 |  |  | 0%
1.2.3 | Staffing requirements | Vendor | 2017-01-12 |  |  | 0%
1.2.4 | Quality Insurance Protocols | Vendor | 2017-01-12 |  |  | 0%
Strategy #3: Develop Policies for Utilization of EBP's | [5 empty] | 0%
1.3.1 | Identify what entity owns the Policy | Vendor |  |  |  | 0%
1.3.2 | Identify where policy will be available | Vendor |  |  |  | 0%
1.3.3 | Determine timeline for policy development | JJOC |  |  |  | 0%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
1.3.5 | Date of policy implementation | JJOC |  |  |  | 0%
Strategy #4: Development of Procedures for Utilization of EBP's | [5 empty] | 0%
1.4.1 | Identify what entity owns the Procedure | Sub Committee |  |  |  | 0%
1.4.2 | Identify where procedure will be available | Sub Committee |  |  |  | 0%
1.4.3 | Determine timeline for procedure development | Sub Committee |  |  |  | 0%
1.4.4 | Determine appropriate review process and approval of procedures | JJOC |  |  |  | 0%
1.4.5 | Date of procedure implementation | JJOC |  |  |  | 0%
Goal #2: Training Program to Enhance EBP's
Strategy #1: Vendor to Develop Training Plan | [5 empty] | 0%
2.1.1 | Training Plan approved by subcommittee | Vendor |  |  |  | 0%
2.1.2 | Training Plan approved by JJOC | JJOC |  |  |  | 0%
Strategy #2: Implementation of Training | [5 empty] | 0%
2.2.1 | Identify who needs training | Vendor & JJOC |  |  |  | 0%
2.2.2 | Develop timeline for training | Vendor & JJOC |  |  |  | 0%
2.2.3 | Identification of ongoing training needs | Vendor & JJOC |  |  |  | 0%
Goal #3: Reporting Requirements for EBP's
Strategy #1: Reports to JJOC | [5 empty] | 0%
3.1.1 | Determine who has oversight and responsibility for report development | Sub Committee |  |  |  | 0%
3.1.2 | Develop Policy specific to reporting requirements | Sub Committee |  |  |  | 0%
3.1.3 | Develop Procedure for frequency of reporting | Sub Committee |  |  |  | 0%
Strategy #2: Quality Assurance | [5 empty] | 0%
3.2.1 | Develop Policies for Quality Improvement Plan for reporting | Vendor and Sub Committee |  |  |  | 0%
3.2.2 | Develop Procedures for Quality Improvement plan for reporting including Corrective Action Plan | Vendor and Sub Committee |  |  |  | 0%
3.2.3 | Select a QA Tool for review | Vendor |  |  |  | 0%
3.2.4 | Training on QA Tool selected | Vendor |  |  |  | 0%
Goal #4: Development and Revisions to 5 Year Strategic Plan
Strategy #1: Authority and Revisions | [5 empty] | 0%
4.1.1 | Determine who has oversight and responsibility for development and revisions to Strategic Plan | JJOC |  |  |  | 0%
4.1.2 | Determine where will strategic plan be published | JJOC |  |  |  | 0%
4.1.3 | Develop Template for 5 yr. Strategic Plan | DCFS
4.1.4 | Develop Template for Annual Report to the 5 yr. Strategic Plan | DCFS |  |  |  | 0%
Strategy #2: Information to be included in 5 Year Plan | [5 empty] | 0%
4.2.1 | Develop specific goals for 5 year plan with measurable benchmarks | Sub Committee |  |  |  | 0%
4.2.2 | Document individual subcommittees, their functions and goals | Sub Committee |  |  |  | 0%
4.2.3 | Develop timeline of implementation with benchmarks | Sub Committee |  |  |  | 0%
4.2.4 | Document reporting requirements | Sub Committee |  |  |  | 0%
4.2.5 | Address Family Engagement Plan | Sub Committee |  |  |  | 0%
4.2.6 | Address Court Findings Prior to Commitment | Sub Committee |  |  |  | 0%
4.2.7 | Address Individual Case Plan | Sub Committee |  |  |  | 0%
4.2.8 | Address Placement of Child | Sub Committee |  |  |  | 0%
4.2.9 | Address Out of State (OOS) Placement of Child | Sub Committee |  |  |  | 0%
4.2.10 | Address Release of Information/Information Sharing | Sub Committee |  |  |  | 0%
4.2.11 | Address System Information Requirements (Data Collection Activities) | Sub Committee |  |  |  | 0%
Strategy #3: Information to be included in Annual Report to Strategic Plan | [5 empty] | 0%
4.3.1 | Document individual subcommittee outcomes | Sub Committee |  |  |  | 0%
4.3.2 | Document completion dates of tasks | Sub Committee |  |  |  | 0%
4.3.3 | Document next steps | Sub Committee |  |  |  | 0%
Strategy #4: Review Process of Strategic Plan | [5 empty] | 0%
4.4.1 | Review by Subcommittee | Sub Committee |  |  |  | 0%
4.4.2 | Review by JJOC | JJOC |  |  |  | 0%
Deliverable #1: 5 Year Strategic Plan
1.1 | Must address everything in 4.2 | Sub Committee
1.2 | Creation of Plan to review the Strategic Plan every 12 months | Sub Committee
1.3 | Creation of Plan to report on the strategic plan to the JJOC and Governor every 12 months | Sub Committee
Deliverable #2: Uniform Standards of Evidence Based Program Use
2.1 | Develop a set of standards | Sub Committee
2.2 | Develop an annual reporting requirement for counties and state on use of evidence based programs and services | Sub Committee
2.3 | Creation of Plan to report on the strategic plan to the JJOC and Governor every 12 months | Sub Committee
2.4 | Provide oversight of Quality Assurance and Corrective action for counties and states in their use of EBP. | Sub Committee

## Risk Asmnt and MH Screen
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Risk Assessment Tool
Strategy #1: Select Risk Assessment Tool | [5 empty] | 100%
1.1.1 | Review available risk assessments | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100% |  | Committee voted to select the YLS as the Risk and Needs Assessment tool on 12/06/2017.Pending JJOC Approval | JJOC voted and approved the use of the YLS.
1.1.2 | Select agreed upon risk assessment tool | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100%
Strategy #2: Training Risk Assessment Tool State-Wide | [5 empty] | 0%
1.2.1 | Identify who needs training | Vendor and JJOC |  |  |  | 0%
1.2.2 | Develop timeline for training | JJOC |  |  |  | 0%
1.2.3 | What entity will own training for Train the Trainer | JJOC |  |  |  | 0%
Strategy #3: Develop State-Wide Policy for Risk Assessment | [5 empty] | 0%
1.3.1 | Identify what entity owns the Policy | Sub Committee |  |  |  | 0%
1.3.2 | Identify where policy will be available | Sub Committee |  |  |  | 0%
1.3.3 | Determine timeline for policy development | Sub Committee |  |  |  | 0%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
1.3.5 | Determine frequency of Risk Assessment | Vendor |  |  |  | 0%
1.3.6 | Date of policy implementation | DCFS |  |  |  | 0%
Strategy #4: Develop Quality Improvement Process for Risk Assessment Tool | [5 empty] | 0%
1.4.1 | Determine who has oversight of Quality Improvement actions | JJOC |  |  |  | 0%
1.4.2 | Develop Quality Improvement guidelines including acceptable standards | Vendor |  |  |  | 0%
1.4.3 | Develop Quality Improve Process | Vendor & Sub Committee |  |  |  | 0%
1.4.4 | Conduct Quality Reviews | DCFS Contractor |  |  |  | 0%
1.4.5 | Determine QA reporting back to JJOC | DCFS and Sub Committee |  |  |  | 0%
Goal #2 - Mental Health Screening Tool
Strategy #1: Select Mental Health Screening Tool | [5 empty] | 100%
2.1.1 | Review available risk assessments | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100% |  | Committee voted to select the MAYSI II as the statewide Mental Health Screening tool on 12/06/2017. Pending JJOC Approval | JJOC voted and approved the use of the MAYSI II
2.1.2 | Select agreed upon risk assessment tool | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100%
Strategy #2: Training Mental Health Screen Tool State-Wide | [5 empty] | 0%
2.2.1 | Identify who needs training | Vendor and JJOC |  |  |  | 0% |  | Note: The MAYSI II vendor may not offer training, what is plan B?
2.2.2 | Develop timeline for training | JJOC |  |  |  | 0%
2.2.3 | What entity will own training for Train the Trainer | JJOC |  |  |  | 0%
Strategy #3: Develop State-Wide Policy for Mental Health Screen | [5 empty] | 0%
2.3.1 | Identify what entity owns the Policy | Sub Committee |  |  |  | 0%
2.3.2 | Identify where policy will be available | Sub Committee |  |  |  | 0%
2.3.3 | Determine timeline for policy development | Sub Committee |  |  |  | 0%
2.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
2.3.5 | Determine frequency of Mental Health Screen | Vendor |  |  |  | 0%
2.3.6 | Date of policy implementation | DCFS |  |  |  | 0%
Strategy #4: Develop Quality Improvement Process for Mental Health Screen | [5 empty] | 0%
2.4.1 | Determine who has oversight of Quality Improvement actions | JJOC |  |  |  | 0%
2.4.2 | Develop Quality Improvement guidelines including acceptable standards | Vendor |  |  |  | 0%
2.4.3 | Develop Quality Improvement Process | Vendor & Sub Committee |  |  |  | 0%
2.4.4 | Conduct Quality Reviews | DCFS Contractor |  |  |  | 0%
2.4.5 | Determine QA reporting back to JJOC | DCFS and Sub Committee |  |  |  | 0%
Goal #3: Caseload PRO Inclusion | [5 empty] | 0%
3.1 | Include the Selected Risk Assessment Tool into Caseload Pro | JJOC/Counties/DCFS |  |  |  | 0%
3.2 | Include the Selected Mental Health Screening Tool into Caseload Pro | JJOC/Counties/DCFS |  |  |  | 0%
3.3 | Determine cost of inclusion and who will fund this | JJOC/Counties/DCFS |  |  |  | 0%
3.4 | Identify reporting requirements for both tools from Caseload PRO | JJOC/Counties/DCFS |  |  |  | 0%
Deliverable #1: Selection of Risk and Needs Assessment
1.1 | Selection of Risk and Needs Assessment Tool for JJOC approval and statewide adoption | Sub Committee
1.2 | Oversee quality assurance activities by DCFS contractor and selected vendor. | Sub Committee
1.3 | Creation of Plan to report on the use of the Risk and Needs Assessment to the JJOC and Governor every 12 months | Sub Committee
1.4 | Determine who will be state trainers of the tool on a go forward basis | Sub Committee
1.5 | Determine training/retraining plan and budgetary issues with travel and resources | Sub Committee
Deliverable #2: Selection of Mental Health Screening Tool
2.1 | Selection of Mental Health Screening Tool for JJOC approval and statewide adoption | Sub Committee
2.2 | Oversee quality assurance activities by DCFS contractor and selected vendor. | Sub Committee
2.3 | Creation of Plan to report on the use of the Mental Health Screening Tool to the JJOC and Governor every 12 months | Sub Committee
2.4 | Determine who will be state trainers of the tool on a go forward basis | Sub Committee
2.5 | Determine training/retraining plan and budgetary issues with travel and resources | Sub Committee

## Data and Perf Measure
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
Develop Performance Measures for Recidivism | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Recidivism
Strategy #1: Recommend Definition for JJOC Adoption | [5 empty] | 18%
1.1.1 | Review Past definitions by Supreme Court Commission | Sub Committee |  |  |  | 90% |  | Reviewed by JJOC | Further discussion needed based on JJOC meeting.
1.1.2 | Determine if revision is needed, if yes, revise definition | Sub Committee |  |  |  | 0%
1.1.3 | Sub Committee Selection or Recommendation to JJOC | Sub Committee |  |  |  | 0%
1.1.4 | JJOC adoption of definition | JJOC and DCFS |  |  |  | 0%
1.1.5 | Inclusion of Definition in Regulation | JJOC and DCFS |  |  |  | 0%
Strategy #2: Develop Performance Measures for Recidivism | [5 empty] | 0%
1.2.1 | Review current accessible data to determine measures | Sub Committee |  |  |  | 0%
1.2.2 | Research what other states are utilizing | Sub Committee |  |  |  | 0%
1.2.3 | Develop reporting mechanism | Sub Committee |  |  |  | 0%
1.2.4 | Determine frequency of reporting | Sub Committee |  |  |  | 0%
1.2.5 | Determine who has oversight of data | JJOC |  |  |  | 0%
1.2.6 | Develop consistent dashboard for reporting purposes | JJOC/Counties/DCFS/Caseload Pro |  |  |  | 0%
Strategy #3: Develop Policies for Recidivism | [5 empty] | 0%
1.3.1 | Identify what entity owns the Policy | Sub Committee or JJOC |  |  |  | 0%
1.3.2 | Identify where policy will be available | Sub Committee or JJOC |  |  |  | 0%
1.3.3 | Determine timeline for policy development | Sub Committee or JJOC |  |  |  | 0%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
1.3.5 | Date of policy implementation | DCFS |  |  |  | 0%
Goal #2: Creation of a Set of Performance Measures
Strategy #1: Points of Measurement | [5 empty] | 0%
2.1.1 | Determine requirement information for state-wide data | Sub Committee |  |  |  | 0%
2.1.2 | Develop required performance measures | Sub Committee |  |  |  | 0%
2.1.3 | Determine who has oversight to requirements | JJOC |  |  |  | 0%
2.1.4 | Determine if performance measures need to be adopted into regulation | JJOC |  |  |  | 0%
Strategy #2: Performance Measures Defined and Policy Development | [5 empty] | 0%
2.2.1 | Define specific measurements | Sub Committee |  |  |  | 0%
2.2.2 | Develop Policy for Performance Measures | Sub Committee |  |  |  | 0%
2.2.3 | Determine who has oversight and is responsible for Policy revisions in the future | Sub Committee |  |  |  | 0%
Goal #3: Quality Improvement Process
Strategy #1: Develop Quality Improvement Process | [5 empty] | 0%
3.1.1 | Determine timeline to validate data | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.2 | Determine what entity will be responsible for data validation | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.3 | Determine frequency validation | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.4 | Develop corrected action plan process | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.5 | Document Quality Improvement Process | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
Deliverable #1: Recidivism
1.1 | Agreed upon definition for JJOC approval and statewide adoption | Sub Committee
1.2 | A set of performance measures to measure recidivism for JJOC approval and statewide adoption | Sub Committee
1.3 | A set of timeframes or ages to measure recidivism for JJOC approval and statewide adoption. (Example: 6 months, 12 months, 18 months, 24 months) | Sub Committee
1.4 | Creation/Development of plan to track youth into the adult system which may include a formal MOU for DOC or data sharing agreement. | Sub Committee
Deliverable #2: Set of Performance Measures
2.1 | Provide a set of performance measures from case initiation to case closure for JJOC approval and statewide adoption | Sub Committee
2.2 | Provide definitions and explanations of what each performance measure is measuring for JJOC approval and statewide adoption | Sub Committee
2.3 | Provide a frequency of reporting for each performance measure. | Sub Committee
Deliverable #3: Data Validation and Quality Assurance
3.1 | Provide a plan for data validation for the counties and state entities to ensure data gather is accurate. | Sub Committee
3.2 | Provide a frequency for data validation reviews. | Sub Committee
3.3 | Determine if MOUs are needed for data validation reviews, if so, provide language | Sub Committee
3.4 | Determine penalties for data errors and level of penalty, if any | Sub Committee

## Youth
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Development of Youth Group
Strategy #1: Selection of Members | [5 empty] | 100%
1.1.1 | Determine mandated positions from AB472 | Governor's Office |  |  |  | 100%
1.1.2 | Governor appoints members | Governor's Office |  |  |  | 100%
1.1.3 | Ensure youth member positions are always filled | JJOC and Governor's Office |  |  |  | 100%
Strategy #2: Process for Continued Participation | [5 empty] | 10%
1.2.1 | Develop strategy to incentivize youth participation | Sub Committee |  |  |  | 10% |  | Ice Breaker Meeting
1.2.2 | Determine budgetary needs if a stipend is offered | JJOC |  |  |  | 10% |  | Potential gas cards
Goal #2 - Communication of Youth Voice
Strategy #1: Determine Areas to Address from Youth Perspective | [5 empty] | 2%
2.1.1 | Select sites to visit | Sub Committee |  |  |  | 10% |  | Reviewed locations
2.1.2 | Schedule site visits |  |  |  |  | 0%
2.1.3 | Develop youth focused areas for focus | Sub Committee |  |  |  | 0%
2.1.4 | Determine potential intercepts | Sub Committee |  |  |  | 0%
2.1.5 | Determine process how areas of focus can be revised | Sub Committee |  |  |  | 0%
Strategy #2: Determine Communication Format | [5 empty] | 0%
2.2.1 | Develop format to provide feedback to JJOC | Sub Committee |  |  |  | 0%
2.2.2 | Determine if there are other avenues and/or platforms to provide education and communication | Sub Committee |  |  |  | 0%
Goal #3 - Youth Education
Strategy #1: Determine How to Educate Community of JJ System | [5 empty] | 0%
3.1.1 | Determine message to communicate to public | Sub Committee |  |  |  | 0%
3.1.2 | Determine how to educate youth community | Sub Committee |  |  |  | 0%
3.1.3 | Determine how to educate adults on youth needs and supports | Sub Committee |  |  |  | 0%
3.1.4 | Determine education needs to law enforcement | Sub Committee |  |  |  | 0%
Strategy #2: Develop Community Partnerships | [5 empty] | 0%
3.2.1 | Determine needs of youth in the community | Sub Committee |  |  |  | 0%
3.2.2 | Develop partnerships with community agencies. | Sub Committee |  |  |  | 0%
3.2.3 | Develop partnerships for supported employment | Sub Committee |  |  |  | 0%
3.2.4 | Develop partnerships for supported educational needs | Sub Committee |  |  |  | 0%
Deliverable #1: Youth Engagement/Participation
1.1 | Determine the best method to engage youth and ensure participation for JJOC approval and statewide adoption | Sub Committee
1.2 | Provide a plan/policy method selected | Sub Committee
Deliverable #2: Youth Voice
2.1 | Provide the JJOC recommendations on areas of youth interests for system improvements based on research and conclusions | Sub Committee
2.2 | Develop a plan/procedure for the committee to address concerns, conduct research, and come to conclusions for presentation to the JJOC | Sub Committee
Deliverable #3: Education
3.1 | Provide plan to communicate/education community entities, brochures, newsletter, etc. | Sub Committee
3.2 | Provide message to communicate to community entities | Sub Committee
3.4 | Provide plan to work with community partners especially in the area of employment of system youth | Sub Committee

## DCFS Plan
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Develop Implementation Team
Strategy #1: Select Members From Parole/Program/Facility | [5 empty] | 100%
1.1.1 | Membership | Deputy | 2017-07-01 | 2017-10-01 | 2017-10-01 | 100% |  | Team Selected
Strategy #2: Implementation Team Work | [5 empty] | 33.33%
1.2.1 | Create Sub Committees | Deputy | 2017-07-01 | 2017-10-01 | 2017-10-01 | 100% |  | Committee Selected
1.2.2 | Assign projects/tasks to sub committee | Committee Chair |  |  |  | 0%
1.2.3 | Schedule ongoing meetings for implementation team |  |  |  |  | 0%
Goal #2: Agency Communication Plan
Strategy #1: DCFS Internal Communication Plan | [5 empty] | 0%
2.1.1 | Communication with Superintendents, Chief of Parole and Chief of Programs Office | DCFS |  |  |  | 0%
2.1.2 | Communication with line staff in facilities, parole and programs office | DCFS |  |  |  | 0%
2.1.3 | Communication with DCFS Deputies on changes | DCFS |  |  |  | 0%
Strategy #2: Determine Messaging | [5 empty] | 0%
2.2.1 | What will be communicated | DCFS |  |  |  | 0%
Strategy #3: Determine Sender and platform | [5 empty] | 0%
2.3.1 | Who will be the primary messenger | DCFS |  |  |  | 0%
2.3.2 | Messenger to deliver in person, road show | DCFS |  |  |  | 0%
Goal #3 - Adoption and Implementation of New Regulations
Strategy #1: Ability to withhold funding for non-compliance of EB Standards | [5 empty] | 0%
3.1.1 | Identify appropriate placement for this/policy or regulation | Administrator and Programs Office |  |  |  | 0%
3.1.2 | Draft language for policy or regulation | Administrator and Programs Office |  |  |  | 0%
Strategy #2: Review and Revise NRS 62H | [5 empty] | 0%
3.2.1 | Review for appropriate language | Administrator and Programs Office |  |  |  | 0%
3.2.2 | Review for appropriate crimes | Administrator and Programs Office |  |  |  | 0%
3.2.3 | Review for reporting requirements | Administrator and Programs Office |  |  |  | 0%
3.2.4 | Add language for reporting requirements | Administrator and Programs Office |  |  |  | 0%
3.2.5 | Draft updated version for review by JJOC | Administrator and Programs Office |  |  |  | 0%
3.2.6 | Determine process for adopting new regulation | Administrator and Programs Office |  |  |  | 0%
Strategy #3: Review and Revise NAC 62H | [5 empty] | 0%
3.3.1 | Review for appropriate language | Administrator and Programs Office |  |  |  | 0%
3.3.2 | Review for appropriate crimes | Administrator and Programs Office |  |  |  | 0%
3.3.3 | Review for reporting requirements | Administrator and Programs Office |  |  |  | 0%
3.3.4 | Add language for reporting requirements | Administrator and Programs Office |  |  |  | 0%
3.3.5 | Draft updated version for review by JJOC | Administrator and Programs Office |  |  |  | 0%
3.3.6 | Determine process for adopting new regulation | Administrator and Programs Office |  |  |  | 0%
Goal #4 - Policy Development (Cross Reference with JJOC Tab)
Strategy #1: Violations of Parole and Revocations
4.1.1 |  | DCFS |  |  |  | 0%
Strategy #2: Placement of Youth Committed to DCFS
4.2.1 |  | DCFS |  |  |  | 0%
Strategy #3: Responses to Violations and Terms of Parole to Court Policy
4.3.1 |  | DCFS |  |  |  | 0%
Strategy #4: Recommendations of Revocation Policy
4.4.1 |  | DCFS |  |  |  | 0%
Strategy #5: Family Engagement Plan
4.5.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Strategy #6: Court Findings Prior to Commitment
4.6.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Strategy #7: Individual Case Plan
4.7.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Strategy #8: Placement of Child
4.8.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Strategy #9: Out of State (OOS) Placement of Child
4.9.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Strategy #10: Release of Information/Information Sharing
4.10.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Strategy #11: System Information Requirements (Data Collection Activities)
4.11.1 |  | JJOC task or JJOC assigns to ? |  |  |  | 0%
Goal #5 - Training Plan
Strategy #1: Petition by Court to Revoke Parole
5.1.1 | [5 empty] | 0%
Strategy #2: Newly created policy training by DCFS and JJOC
5.2.1 | [5 empty] | 0%
Deliverable #1: Policy Development and Adoption
1.1 | Violations of Parole and Revocations | DCFS
1.2 | Placement of Youth Committed to DCFS | DCFS
1.3 | Responses to Violations and Terms of Parole to Court Policy | DCFS
1.4 | Recommendations of Revocation Policy | DCFS
| Family Engagement Plan | JJOC task or JJOC assigns to ?
| Court Findings Prior to Commitment | JJOC task or JJOC assigns to ?
| Individual Case Plan | JJOC task or JJOC assigns to ?
| Placement of Child | JJOC task or JJOC assigns to ?
| Out of State (OOS) Placement of Child | JJOC task or JJOC assigns to ?
| Release of Information/Information Sharing | JJOC task or JJOC assigns to ?
| System Information Requirements (Data Collection Activities) | JJOC task or JJOC assigns to ?
Deliverable #2: Communication Plan
2.1 | Provide a comprehensive DCFS communication plan to address new changes | DCFS
2.2 | Determine the messaging | DCFS
2.3 | Determine who will be communicating and how | DCFS
Deliverable #3: New Regulations
3.1 | Recidivism | Leslie/Alexis
3.2 | NRS 62 H | Leslie/Alexis
3.3 | NAC 62 H | Leslie/Alexis
3.4 | Strategic Plan | Leslie/Alexis
3.5 | Performance Measures | Leslie/Alexis
3.6 | Evidence Based Standards | Leslie/Alexis