## JJOC
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Establish Standard Procedures for Measuring Outcomes
Strategy #1: Identify Outcomes measures | [5 empty] | 100%
1.1.1 | Establish outcomes measures for statewide system improvement measures | JJOC | 2017-12-15 | 2018-06-30 |  | 100%
Goal #2 - Reporting Requirements of JJOC and DCFS
Strategy #1: Annual LCB Compliance Report 2018 | [5 empty] | 100%
2.1.1 | Create a template | JJOC | 2017-12-15 | 2018-01-31 | 2018-01-30 | 100%
2.1.2 | Establish ownership of this report | JJOC | 2017-12-15 | 2017-12-15 | 2017-12-15 | 100%
2.1.3 | Submit completed report | JJOC | 2017-12-15 | 2018-01-31 | 2018-01-30 | 100%
2.1.4 | Submit final report to Governor's office | JJOC | 2017-12-15 | 2018-01-31 | 2018-01-30 | 100%
Strategy #2: Annual Report to the Governor 2018 | [5 empty] | 100%
2.2.1 | Create a template | JJOC | 2017-12-15 | 2018-07-01 |  | 100%
2.2.2 | Establish ownership of this report | JJOC | 2017-12-15 | 2018-07-01 |  | 100%
2.2.3 | Submit completed report | JJOC | 2017-12-15 | 2018-07-01 |  | 100%
2.2.4 | Submit final report to LCB | JJOC | 2017-12-15 | 2018-07-01 |  | 100%
Strategy #3: Annual LCB Compliance Report 2019 | [5 empty] | 50%
2.3.1 | Create a template | JJOC | 2018-12-01 | 2019-01-31 |  | 100%
2.3.2 | Establish ownership of this report | JJOC | 2018-12-01 | 2019-01-31 |  | 100%
2.3.3 | Submit completed report | JJOC | 2018-12-01 | 2019-01-31 |  | 0%
2.3.4 | Submit final report to Governor's office | JJOC | 2018-12-01 | 2019-01-31 |  | 0%
Strategy #4: Annual Report to the Governor 2019 | [5 empty] | 50%
2.4.1 | Create a template | JJOC | 2018-12-01 | 2019-07-01 |  | 100%
2.4.2 | Establish ownership of this report | JJOC | 2018-12-01 | 2019-07-01 |  | 100%
2.4.3 | Submit completed report | JJOC | 2018-12-01 | 2019-07-01 |  | 0%
2.4.4 | Submit final report to LCB | JJOC | 2018-12-01 | 2019-07-01 |  | 0%
Goal #3 - Annual Quality Assurance Review
Strategy #1: Quality Assurance Tool | [5 empty] | 100%
3.1.1 | JJOC must select QA Tool | Kelly Wooldridge | 2017-12-05 | 2018-06-30 |  | 100% |  | CPC Instrument
3.1.2 | JJOC to receive training on use of tool | JJOC | 2018-04-05 | 2018-07-01 |  | 100% |  | Training completed week of June 25th | Contract Executed
3.1.3 | Determine who will be responsible for conducting review | DCFS | 2018-02-07 | 2018-07-01 |  | 100% |  | 8 Individuals trained and are going through the certification process.
Strategy #2: Utilization of Tool and Review Process | [5 empty] | 31.25%
3.2.1 | Determine timeline of each facility review | DCFS |  | 2019-07-01 |  | 50% |  | Dependent on assessor certification
3.2.2 | Develop procedures for use of QA Review Tool | DCFS |  | 2019-07-01 |  | 25%
3.2.3 | Develop procedures for Quality Improvement Plan | DCFS |  | 2019-07-01 |  | 25%
3.2.4 | Develop procedures for JJOC to review QA Reviews from facilities | DCFS |  | 2019-07-01 |  | 25%
Goal #4 - Adoption and Implementation of New Regulations
Strategy #1: Ability to withhold funding for non-compliance of EB Standards | [5 empty] | 33.33%
4.1.1 | Identify appropriate placement for this/policy or regulation | DCFS/JJOC |  | 2019-07-01 |  | 50% |  | Oversight to remain with funding source
4.1.2 | Draft language for policy or regulation | DCFS/JJOC |  | 2019-07-01 |  | 50% |  | Being reviewed internally
4.1.3 | Policy review and approval by JJOC | JJOC |  | 2019-07-01 |  | 0%
Strategy #2: Review and Revise NRS 62H | [5 empty] | 62.5%
4.2.1 | Review for appropriate language | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.2.2 | Review for appropriate crimes | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.2.3 | Review for reporting requirements | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.2.4 | Add language for reporting requirements | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.2.5 | Draft updated version for review by JJOC | DCFS/JJOC |  | 2018-07-01 |  | 50% |  | Being reviewed internally
4.2.6 | Determine process for adopting new regulation | JJOC |  | 2018-07-01 |  | 25%
Strategy #3: Review and Revise NAC 62H | [5 empty] | 62.5%
4.3.1 | Review for appropriate language | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.3.2 | Review for appropriate crimes | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.3.3 | Review for reporting requirements | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.3.4 | Add language for reporting requirements | DCFS/JJOC |  | 2018-07-01 |  | 75%
4.3.5 | Draft updated version for review by JJOC | DCFS/JJOC |  | 2018-07-01 |  | 50% |  | Being reviewed internally
4.3.6 | Determine process for adopting new regulation | JJOC |  | 2018-07-01 |  | 25%
Goal #5 - Development of By-Laws and Participation Requirements | [5 empty] | 100%
5.1 | Develop By-Laws for JJOC | Joey, Kelly, Katie | 2018-01-12 | 2018-02-28 |  | 100% |  | JJOC Approved 4/13/18
5.2 | Determine participation requirements | JJOC |  | 2018-06-30 |  | 100%
5.3 | Review By-Laws | JJOC |  | 2018-06-30 |  | 100%
5.4 | Approve By-Laws | JJOC |  | 2018-06-30 |  | 100%
Goal #6: Policy Development (Cross Reference DCFS Tab)
Strategy #1: Violations of Parole and Revocation | [5 empty] | 50%
6.1.1 | JJOC Review of Policy | JJOC |  |  |  | 100%
6.1.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #2: Placement of Youth Committed to DCFS/ Admission Determination Procedure | [5 empty] | 50%
6.2.1 | JJOC Review of Policy | JJOC |  |  |  | 100%
6.2.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #3: Family Engagement Plan | [5 empty] | 0%
6.3.1 | JJOC Review of Policy | JJOC |  |  |  | 0%
6.3.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy # 4: Court Finidings Prior to Committment | [5 empty] | 50%
6.4.1 | JJOC Review of Policy | JJOC |  |  |  | 100%
6.4.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #5: Individual Case Plan and Discharge Planning/Re-Entry | [5 empty] | 0%
6.5.1 | JJOC Review of Policy | JJOC |  |  |  | 0%
6.5.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #6: Out of State (OOS) Placement of Children | [5 empty] | 0%
6.6.1 | JJOC Review of Policy | JJOC |  |  |  | 0%
6.6.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #7:Release of Information/ Information Sharing | [5 empty] | 50%
6.7.1 | JJOC Review of Policy | JJOC |  |  |  | 100%
6.7.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #8: System Information Requirements (Data Collection Activities) | [5 empty] | 0%
6.8.1 | JJOC Review of Policy | JJOC |  |  |  | 0%
6.8.2 | JJOC Review of SOP | JJOC |  |  |  | 0%
Strategy #9: Length of Stay | [5 empty] | 50%
6.9.1 | JJOC Review of Policy | JJOC |  |  |  | 100%
6.9.2 | JJOC Review of SOP | JJOC |  |  |  | 0%

## Strategic Plan
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Evidence Based Practices
Strategy #1: Vendor Procurement for Resource Center | [5 empty] | 100%
1.1.1 | Develop RFP to select a vendor for EBP Resource Center | DCFS | 2017-09-28 | 2017-11-16 | 2017-11-16 | 100% |  | Selection Made | 3 vendor applications received
1.1.2 | Evaluation and selection of Vendor | State Purchasing | 2017-11-16 | 2017-11-16 | 2017-11-16 | 100% |  | Selection Made | Evaluation committee of 4; selection made
1.1.3 | Contract development | State Purchasing | 2017-11-16 | 2017-12-15 |  | 100%
1.1.4 | BOE Review of Contract | State Purchasing | 2017-11-16 | 2017-02-13 |  | 100%
1.1.5 | Establish Invoice Process | Brian Dahlberg | 2018-01-12 | 2018-02-13 |  | 100%
Strategy #2: Selection of EBP Models by Vendor | [5 empty] | 50%
1.2.1 | Vendor to identify appropriate EBP's for state-wide utilization | Vendor | 2017-01-12 | ongoing |  | 50% |  | Survey sent out 4/30/18; Meeting with center on June 4th
1.2.2 | Determine uniform standards that EBP must follow | Sub committee | 2017-01-12 | 2018-07-01 |  | 100% |  | See Matrix
1.2.3 | Staffing requirements | Vendor | 2017-01-12 | ongoing |  | 25% |  | Dependent on EBP's and ongoing funding
1.2.4 | Quality Assurance Protocols | Vendor | 2017-01-12 | ongoing |  | 25% |  | Will be specfic to each EBP
Strategy #3: Develop Policies and Procedures for Utilization of EBP's | [5 empty] | 27%
1.3.1 | Identify what entity owns the Policy and Procedures | JJOC |  | ongoing |  | 50%
1.3.2 | Identify where policy and procedures will be available | JJOC |  | ongoing |  | 50%
1.3.3 | Determine timeline for policy and procedure development | JJOC |  | ongoing |  | 10%
1.3.4 | Determine appropriate review process and approval of policy and procedures | JJOC |  | ongoing |  | 25%
1.3.5 | Date of policy and procedure implementation | JJOC |  |  |  | 0%
Goal #2: Training Program to Enhance EBP's
Strategy #1: Vendor to Develop Training Plan | [5 empty] | 5%
2.1.1 | Training Plan approved by subcommittee | Vendor |  | ongoing |  | 10%
2.1.2 | Training Plan approved by JJOC | JJOC |  |  |  | 0%
Strategy #2: Implementation of Training | [5 empty] | 50%
2.2.1 | Identify who needs training | Vendor & JJOC |  | 2018-07-01 |  | 100%
2.2.2 | Develop timeline for training | Vendor & JJOC |  | ongoing |  | 25% |  | Dependent on EBP's and ongoing funding
2.2.3 | Identification of ongoing training needs | Vendor & JJOC |  | ongoing |  | 25%
Goal #3: Reporting Requirements for EBP's
Strategy #1: Reports to JJOC | [5 empty] | 50%
3.1.1 | Determine who has oversight and responsibility for report development | Sub Committee |  | 2018-07-01 |  | 100% |  | JJOC, Resource Center
3.1.2 | Develop Policy specific to reporting requirements | Sub Committee |  |  |  | 25% |  | Will be finalized after approval of performance measures/Strategic Plan
3.1.3 | Develop Procedure for frequency of reporting | Sub Committee |  |  |  | 25%
Strategy #2: Quality Assurance | [5 empty] | 50%
3.2.1 | Develop Policies for Quality Improvement Plan for reporting | Vendor and Sub Committee |  |  |  | 25%
3.2.2 | Develop Procedures for Quality Improvement plan for reporting including Corrective Action Plan | Vendor and Sub Committee |  |  |  | 25%
3.2.3 | Select a QA Tool for review | JJOC |  |  |  | 100% |  | Assesses facilities use of EBP's
3.2.4 | Training on QA Tool selected | QA Vendor |  |  |  | 50%
Goal #4: Development and Revisions to 5 Year Strategic Plan
Strategy #1: Authority and Revisions | [5 empty] | 100%
4.1.1 | Determine who has oversight and responsibility for development and revisions to Strategic Plan | JJOC |  | 2018-07-01 |  | 100%
4.1.2 | Determine where will strategic plan be published | JJOC |  | 2018-07-01 |  | 100% |  | DCFS website
4.1.3 | Develop Template for 5 yr. Strategic Plan | DCFS |  | 2018-07-01 |  | 100%
4.1.4 | Develop Template for Annual Report to the 5 yr. Strategic Plan | DCFS |  | 2018-07-01 |  | 100% |  | JJOC approved 8.10.14
Strategy #2: Information to be included in 5 Year Plan | [5 empty] | 100%
4.2.1 | Develop specific goals for 5 year plan with measurable benchmarks | Sub Committee |  | 2018-07-01 |  | 100%
4.2.2 | Document individual subcommittees, their functions and goals | Sub Committee |  | 2018-07-01 |  | 100%
4.2.3 | Develop timeline of implementation with benchmarks | Sub Committee |  | 2018-07-01 |  | 100%
4.2.4 | Document reporting requirements | Sub Committee |  | 2018-07-01 |  | 100%
4.2.5 | Address Family Engagement Plan | Sub Committee |  | 2018-07-01 |  | 100%
4.2.6 | Address Court Findings Prior to Commitment | Sub Committee |  | 2018-07-01 |  | 100%
4.2.7 | Address Individual Case Plan | Sub Committee |  | 2018-07-01 |  | 100%
4.2.8 | Address Placement of Child | Sub Committee |  | 2018-07-01 |  | 100%
4.2.9 | Address Out of State (OOS) Placement of Child | Sub Committee |  | 2018-07-01 |  | 100%
4.2.10 | Address Release of Information/Information Sharing | Sub Committee |  | 2018-07-01 |  | 100%
4.2.11 | Address System Information Requirements (Data Collection Activities) | Sub Committee |  | 2018-07-01 |  | 100%
Strategy #3: Information to be included in Annual Report to Strategic Plan | [5 empty] | 100%
4.3.1 | Document individual subcommittee outcomes | Sub Committee |  | ongoing |  | 100%
4.3.2 | Document completion dates of tasks | Sub Committee |  | ongoing |  | 100%
4.3.3 | Document next steps | Sub Committee |  | ongoing |  | 100%
Strategy #4: Review Process of Strategic Plan | [5 empty] | 100%
4.4.1 | Review by Subcommittee | Sub Committee |  | 2018-07-01 |  | 100% |  | 2018-05-31
4.4.2 | Review by JJOC | JJOC |  | 2018-07-01 |  | 100% |  | 2018-06-08

## Risk Asmnt and MH Screen
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Risk Assessment Tool
Strategy #1: Select Risk Assessment Tool | [5 empty] | 100%
1.1.1 | Review available risk assessments | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100% |  | Committee voted to select the YLS as the Risk and Needs Assessment tool on 12/06/2017.Pending JJOC Approval | JJOC voted and approved the use of the YLS.
1.1.2 | Select agreed upon risk assessment tool | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100%
Strategy #2: Training Risk Assessment Tool State-Wide | [5 empty] | 100%
1.2.1 | Identify who needs training | Vendor and JJOC |  | 2018-07-01 |  | 100%
1.2.2 | Develop timeline for training | JJOC |  | 2019-07-01 |  | 100%
1.2.3 | What entity will own training for Train the Trainer | JJOC |  | 2018-07-01 |  | 100% |  | DCFS
Strategy #3: Develop State-Wide Policy for Risk Assessment | [5 empty] | 95.83%
1.3.1 | Identify what entity owns the Policy | Sub Committee |  | 2018-07-01 |  | 100% |  | DCFS
1.3.2 | Identify where policy will be available | Sub Committee |  | 2018-07-01 |  | 100% |  | DCFS Website
1.3.3 | Determine timeline for policy development | Sub Committee |  | 2018-07-01 |  | 100%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  | 2018-07-01 |  | 100% |  | DCFS/JJOC Approval
1.3.5 | Determine frequency of Risk Assessment | Vendor |  | 2019-07-01 |  | 100%
1.3.6 | Date of policy implementation | DCFS |  | 2019-07-01 |  | 75%
Strategy #4: Develop Quality Improvement Process for Risk Assessment Tool | [5 empty] | 60%
1.4.1 | Determine who has oversight of Quality Improvement actions | JJOC |  | 2018-07-01 |  | 100% |  | JJOC
1.4.2 | Develop Quality Improvement guidelines including acceptable standards | Vendor |  | 2019-07-01 |  | 100%
1.4.3 | Develop Quality Improve Process | Vendor & Sub Committee |  | 2019-07-01 |  | 50%
1.4.4 | Conduct Quality Reviews | DCFS Contractor |  | 2019-07-01 |  | 0%
1.4.5 | Determine QA reporting back to JJOC | DCFS and Sub Committee |  | 2019-07-01 |  | 50%
Goal #2 - Mental Health Screening Tool
Strategy #1: Select Mental Health Screening Tool | [5 empty] | 100%
2.1.1 | Review available risk assessments | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100% |  | Committee voted to select the MAYSI II as the statewide Mental Health Screening tool on 12/06/2017. Pending JJOC Approval | JJOC voted and approved the use of the MAYSI II
2.1.2 | Select agreed upon risk assessment tool | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100%
Strategy #2: Training Mental Health Screen Tool State-Wide | [5 empty] | 75%
2.2.1 | Identify who needs training | Vendor and JJOC |  | 2018-07-01 |  | 100%
2.2.2 | Develop timeline for training | JJOC |  | 2019-07-01 |  | 25%
2.2.3 | What entity will own training for Train the Trainer | JJOC |  | 2018-07-01 |  | 100% |  | DCFS/JJOC
Strategy #3: Develop State-Wide Policy for Mental Health Screen | [5 empty] | 83.33%
2.3.1 | Identify what entity owns the Policy | Sub Committee |  | 2018-07-01 |  | 100% |  | DCFS/JJOC
2.3.2 | Identify where policy will be available | Sub Committee |  | 2018-07-01 |  | 100% |  | DCFS Website
2.3.3 | Determine timeline for policy development | Sub Committee |  | 2019-07-01 |  | 25%
2.3.4 | Determine appropriate review process and approval of policy | JJOC |  | 2018-07-01 |  | 100% |  | DCFS/JJOC
2.3.5 | Determine frequency of Mental Health Screen | Vendor |  | 2019-07-01 |  | 100%
2.3.6 | Date of policy implementation | DCFS |  | 2019-07-01 |  | 75%
Strategy #4: Develop Quality Improvement Process for Mental Health Screen | [5 empty] | 40%
2.4.1 | Determine who has oversight of Quality Improvement actions | JJOC |  | 2018-07-01 |  | 100% |  | DCFS/JJOC
2.4.2 | Develop Quality Improvement guidelines including acceptable standards | Vendor |  | 2019-07-01 |  | 25%
2.4.3 | Develop Quality Improvement Process | Vendor & Sub Committee |  | 2019-07-01 |  | 25%
2.4.4 | Conduct Quality Reviews | DCFS Contractor |  | 2019-07-01 |  | 25%
2.4.5 | Determine QA reporting back to JJOC | DCFS and Sub Committee |  | 2019-07-01 |  | 25%
Goal #3: Caseload PRO Inclusion | [5 empty] | 75%
3.1 | Include the Selected Risk Assessment Tool into Caseload Pro | JJOC/Counties/DCFS |  | 2018-07-01 |  | 75% |  | MHS provided the tool and coding to CLP. Waiting for upload from CLP after BOE approval in May. | Programming of YLS into CLP in progress.
3.2 | Include the Selected Mental Health Screening Tool into Caseload Pro | JJOC/Counties/DCFS |  | 2018-07-01 |  | 100%
3.3 | Determine cost of inclusion and who will fund this | JJOC/Counties/DCFS |  | 2018-07-01 |  | 100%
3.4 | Identify reporting requirements for both tools from Caseload PRO | JJOC/Counties/DCFS |  | 2018-12-01 |  | 25%

## Data and Perf Measure
DATA ENTRY ON THIS PAGE ONLY |  |  |  |  | SAG
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
Develop Performance Measures for Recidivism | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Recidivism
Strategy #1: Recommend Definition for JJOC Adoption | [5 empty] | 100%
1.1.1 | Review Past definitions by Supreme Court Commission | Sub Committee |  |  |  | 100% |  | Reviewed by JJOC | Further discussion needed based on JJOC meeting.
1.1.2 | Determine if revision is needed, if yes, revise definition | Sub Committee |  | 2018-03-31 |  | 100% |  | Revised 3/1/18 by Data Subcommittee
1.1.3 | Sub Committee Selection or Recommendation to JJOC | Sub Committee |  |  |  | 100% |  | Will present at 3/9/18 JJOC Meeting.
1.1.4 | JJOC adoption of definition | JJOC and DCFS |  |  |  | 100% |  | JJOC approval on 3/9/18.
1.1.5 | Inclusion of Definition in Regulation | JJOC and DCFS |  | 2018-07-01 |  | 100% |  | Decided not to include at 5/31 meeting since in Strategic Plan
Strategy #2: Develop Performance Measures for Recidivism | [5 empty] | 95.45%
1.2.1 | Review current accessible data to determine measures | Sub Committee |  | 2018-07-01 |  | 100%
1.2.2 | Research what other states are utilizing | Sub Committee |  | 2018-07-01 |  | 100%
1.2.3 | Develop reporting mechanism | Sub Committee |  | 2018-07-01 |  | 100% |  | CLP when up and running; as outlined by 62H
1.2.4 | Determine frequency of reporting | Sub Committee |  | 2018-07-01 |  | 100% |  | Annual
1.2.5 | Determine who has oversight of data | JJOC |  | 2018-07-01 |  | 100% |  | JJOC
1.2.6 | Develop consistent dashboard for reporting purposes | JJOC/Counties/DCFS/Caseload Pro |  | ongoing |  | 50% |  | Ongoing work with CLP
1.2.7 | Measurement point: Re-arrested | Sub Committee | 2018-02-07 | 2018-07-01 |  | 100%
1.2.8 | Measurement point: Re-adjudicated | Sub Committee | 2018-02-07 | 2018-07-01 |  | 100%
1.2.9 | Measurement point: Re-committed | Sub Committee | 2018-02-07 | 2018-07-01 |  | 100%
1.2.10 | Measurement point: In violation of Supervision | Sub Committee | 2018-02-07 | 2018-07-01 |  | 100%
1.2.11 | Measurement point: Convicted by an Adult Court | Sub Committee | 2018-02-07 | 2018-07-01 |  | 100%
Strategy #3: Develop Policies for Recidivism | [5 empty] | 90%
1.3.1 | Identify what entity drafts the Policy and who has oversight | Sub Committee or JJOC |  | 2018-07-01 |  | 100% |  | DCFS will draft the policy; JJOC will have oversight
1.3.2 | Identify where policy will be available | Sub Committee or JJOC |  | 2018-07-01 |  | 100% |  | DCFS Website
1.3.3 | Determine timeline for policy development | Sub Committee or JJOC |  | 2018-07-01 |  | 100% |  | Will begin work ASAP
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  | 2018-07-01 |  | 100% |  | Will go to June JJOC for approval
1.3.5 | Date of policy implementation | DCFS |  | 2018-07-01 |  | 50% |  | 2018-07-01
Goal #2: Creation of a Set of Performance Measures
Strategy #1: Points of Measurement | [5 empty] | 100%
2.1.1 | Determine requirement information for state-wide data | Sub Committee |  | 2018-07-01 |  | 100%
2.1.2 | Develop required performance measures | Sub Committee |  | 2018-07-01 |  | 100% |  | Family Engagement, Room confinement, Rates of Disciplinary Action, Education, Vocation - Will use the Risk Level of the YLS in the 8 domains + Recidivism
2.1.3 | Determine who has oversight to requirements | JJOC |  | 2018-07-01 |  | 100% |  | JJOC
2.1.4 | Determine if performance measures need to be adopted into regulation | JJOC |  | 2018-07-01 |  | 100% |  | Currently in statute and in PBS requirements
2.1.5 | Measurement point: By Facility (group home, RTC, youth camp, state correctionsl) |  |  | 2018-07-01 |  | 100%
2.1.6 | Measurement point: By Service Provider |  |  | 2018-07-01 |  | 100%
2.1.7 | Measurement point: By the Parole/Probation Services |  |  | 2018-07-01 |  | 100% |  | Measures up for vote at June 8 JJOC
2.1.8 | Measurement point: By County |  |  | 2018-07-01 |  | 100%
Strategy #2: Performance Measures Defined and Policy Development | [5 empty] | 83.33%
2.2.1 | Define specific measurements | Sub Committee |  | 2018-07-01 |  | 100% |  | YLS Overall Risk Score, Score in 8 domains of YLS, Breakdown of Diversion data, Data measures required by juvenile courts
2.2.2 | Develop Policy for Performance Measures | DCFS |  | 2019-07-01 |  | 50%
2.2.3 | Determine who has oversight and is responsible for Policy revisions in the future | Sub Committee |  | 2018-07-01 |  | 100% |  | DCFS/JJOC
Goal #3: Quality Improvement Process
Strategy #1: Develop Quality Improvement Process | [5 empty] | 22%
3.1.1 | Determine timeline to validate data | JJOC/Sub Committee and DCFS Contractor |  | 2019-07-01 |  | 25%
3.1.2 | Determine what entity will be responsible for data validation | JJOC/Sub Committee and DCFS Contractor |  | 2019-07-01 |  | 25%
3.1.3 | Determine frequency validation | JJOC/Sub Committee and DCFS Contractor |  | 2019-07-01 |  | 25%
3.1.4 | Develop corrected action plan process | JJOC/Sub Committee and DCFS Contractor |  | 2019-07-01 |  | 25%
3.1.5 | Document Quality Improvement Process | JJOC/Sub Committee and DCFS Contractor |  | 2019-07-01 |  | 10%

## Youth
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Development of Youth Group
Strategy #1: Selection of Members | [5 empty] | 100%
1.1.1 | Determine mandated positions from AB472 | Governor's Office |  |  |  | 100%
1.1.2 | Governor appoints members | Governor's Office |  |  |  | 100%
1.1.3 | Ensure youth member positions are always filled | JJOC and Governor's Office |  |  |  | 100%
Strategy #2: Process for Continued Participation | [5 empty] | 10%
1.2.1 | Develop strategy to incentivize youth participation | Sub Committee |  |  |  | 10% |  | Ice Breaker Meeting | No meeting held in March. Will updated after 4/11/18 meeting.
1.2.2 | Determine budgetary needs if a stipend is offered | JJOC |  |  |  | 10% |  | Potential gas cards
Goal #2 - Communication of Youth Voice
Strategy #1: Determine Areas to Address from Youth Perspective | [5 empty] | 35%
2.1.1 | Select sites to visit | Sub Committee |  |  | ongoing | 100% |  | Reviewed locations
2.1.2 | Schedule site visits | Sub Committee |  |  | ongoing | 75% |  | Murphy Bernadini site visit 3/9/18; Jan Evans visit on 9/11/18 | Next site visits 11.13.18 and 11.14.18 at Caliente, Summit View and CCDC
2.1.3 | Develop youth focused areas for focus | Sub Committee |  |  |  | 0%
2.1.4 | Determine potential intercepts | Sub Committee |  |  |  | 0%
2.1.5 | Determine process how areas of focus can be revised | Sub Committee |  |  |  | 0%
Strategy #2: Determine Communication Format | [5 empty] | 50%
2.2.1 | Develop format to provide feedback to JJOC | Sub Committee |  |  |  | 100%
2.2.2 | Determine if there are other avenues and/or platforms to provide education and communication | Sub Committee |  |  |  | 0% |  | participation in other committees

## SAG
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Compliance with the Juvenile Justice Delinquency Preventon Act (JJDPA)
Strategy #1: Maintain Compliance With The Act | [5 empty] | 100%
1.1.1 | Establish State authority to do this - By Exective Order - there have been at least 4 EO's since the 1980's | Governor |  | 2017-12-17 |  | 100%
Goal #2 - Title II Formula Grant
Strategy #1: Grant Solicitation and Grant Application | [5 empty] | Annual
2.1.1 | OJJDP Sends Grant Solicitation | OJJDP - Feds | Annual |  | ongoing | January - March
2.1.2 | Programs Office Staff prepare grant application and all supporting documentation | Chief | Annual |  | ongoing | January - May
2.1.3 | SAG Planning Committee Reviews | Chief and SAG | Annual |  | ongoing | April - May
2.1.4 | SAG Planning Committee Approves | Chief and SAG | Annual |  | ongoing | April - May
2.1.5 | SAG and Programs Office Staff verify all 28 compliance areas met | Chief and SAG | Annual |  | ongoing | April - May
2.1.6 | JJOC Approves | JJOC | Annual |  | ongoing | April - May
2.1.7 | DCFS Administrator signs | Administrator | Annual |  | ongoing | April - May
2.1.8 | Programs Office Staff submits application | Chief | Annual |  | ongoing | May
2.1.9 | OJJDP notifies State of award - money is initially frozen | OJJDP - Feds | Annual |  | ongoing | September - October
2.1.10 | Programs Office Staff clarifies and submits additional information | Chief | Annual |  | ongoing | October - December
2.1.11 | OJJDP unfreezes funds | OJJDP - Feds | Annual |  | ongoing | October - December
2.1.12 | Programs Office Staff completes bi-annual grant reports and performance measure matrices | Chief | Annual |  | ongoing | March and September
Strategy #2: State Advisory Group | [5 empty] | Annual
2.2.1 | Executive Order outlines State's authority | Governor | Annual |  | ongoing
2.2.2 | Governor Appoints members - must meet OJJDP standards | Governor | Annual |  | ongoing | As Needed
2.2.3 | Meets quarterly at a minimum | SAG and Chief | Annual |  | ongoing
Strategy #3: Grant Process - RFP and Sub Grants | [5 empty] | Annual
2.3.1 | Programs Office Staff submits application | Chief | Annual |  | ongoing | May
2.3.2 | Programs Office Staff prepares RFP | Chief | Annual |  | ongoing | May
2.3.3 | Programs Office Staff receive applications for grant funding | Chief | Annual |  | ongoing | June
2.3.4 | Programs Office Staff sets up grant committee meeting | Support Staff | Annual |  | ongoing | June
2.3.5 | Programs Office Staff prepares and send applications received to SAG | Support Staff | Annual |  | ongoing | June
2.3.6 | SAG meets to fund sub grantees | Chief, SAF, Support Staff | Annual |  | ongoing | June
2.3.7 | SAG prepares a grant slate | SAG and Chief | Annual |  | ongoing | June
2.3.8 | SAG Submits grant slate to JJOC for approval | JJOC | Annual |  | ongoing | July
2.3.9 | Programs Office Staff sends grant award letters based on approved grant slate | Chief | Annual |  | ongoing | July
2.3.10 | Programs Office Staff prepares and sends quarterly reports to sub grantees | Chief | Annual |  | ongoing | July
2.3.11 | Programs Office Staff monitors sub grantees throughout the year | Chief | Annual |  | ongoing | Ongoing
2.3.12 | Programs Office Staff gathers data on performance measures from sub grantees annually | Chief | Annual |  | ongoing | Ongoing
2.3.13 | QA activities may be conducted annually on any sub grantee | Chief | Annual |  | ongoing | As needed
2.3.14 | SAG monitors performance through DCFS updates | Chief | Annual |  | ongoing | Quarterly Meetings
Strategy #4: Annual Report to the Governor | [5 empty] | Annual
2.4.1 | Programs Office Staff creates draft, usually in April | Chief | Annual | Started | ongoing | April - June |  | SAG to review at June 14th meeting
2.4.2 | SAG Planning Committee Reviews | SAG and Chief | Annual |  | ongoing | April - June
2.4.3 | SAG Planning Committee Approves | SAG and Chief | Annual |  | ongoing | April - June
2.4.4 | Revisions Made | Chief | Annual |  | ongoing | April - June
2.4.5 | JJOC Approves | JJOC | Annual |  | ongoing | April - June
2.4.6 | Final version created and sent to the Governor's office | Chief | Annual |  | ongoing | April - June
Strategy #5: Annual DMC Report | [5 empty] | Annual
2.5.1 | Programs Office Staff prepares annual template | Chief | Annual | 2018-03-27 | ongoing | November
2.5.2 | Programs Office Staff sends template to counties | Chief | Annual | 2018-03-27 | ongoing | December
2.5.3 | Counties provide data | Counties | Annual | 2018-03-27 | ongoing | January
2.5.4 | Programs Office Staff compiles data | Chief | Annual | 2018-03-27 | ongoing | January - March
2.5.5 | Programs Office Staff writes annual report | Chief | Annual | 2018-03-27 | ongoing | February - March
2.5.6 | Programs Office Staff update RRI Federal Platform | Chief | Annual | 2018-03-27 | ongoing | February - March
2.5.7 | SAG Reviews Report | SAG and Chief | Annual | 2018-03-27 | ongoing | February - March
2.5.8 | Report submittted as part of Anuual Federal Compliance Report | Chief | Annual | 2018-03-27 | ongoing | March - April
Strategy #6: Compliance with Jail Removal/Sight & Sound Separation/DSO | [5 empty] | Annual
2.6.1 | Programs Office Staff gathers data from juvenile detention facilities and adult jails | Support Staff | Annual | 2018-03-27 | ongoing | Ongoing
2.6.2 | Programs Office Staff updates Compliance Manual and Compliance Plan | Chief | Annual | 2018-03-27 | ongoing | July - November
2.6.3 | Programs Office Staff updates annual self report survey's | Chief | Annual | 2018-03-27 | ongoing | July - November
2.6.4 | Programs Office Staff verifies compliance universe (adult and juvenile facilities/courts) | Chief and Support Staff | Annual | 2018-03-27 | ongoing | July - November
2.6.5 | SAG reviews review Compliance Manual/Plan/Survey documents | SAG and Chief | Annual | 2018-03-27 | ongoing | October
2.6.6 | Programs Office Staff sends out annual survey's to roughly 310 Nevada facilities | Support Staff | Annual | 2018-03-27 | ongoing | November
2.6.7 | Survey Data Collection | Support Staff | Annual | 2018-03-27 | ongoing | November - February
2.6.8 | Programs Office Staff + Contractor visit roughly 35% of the 310 facilities annually | Chief, Contractor, Support Staff | Annual | 2018-03-27 | ongoing | November - February
2.6.9 | Programs Office staff pulls report from annual collection of data from adult jails and juvenile detention facilities | Chief | Annual | 2018-03-27 | ongoing | November - February
2.6.10 | SAG receives updates on compliance progress at meetings | SAG and Chief | Annual | 2018-03-27 | ongoing | Ongoing
2.6.11 | SAG Reviews Report - May or may not provide updates | SAG and Chief | Annual | 2018-03-27 | ongoing | Ongoing
2.6.12 | Report submitted as part of Annual Federal Compliance Report | Chief | Annual | 2018-03-27 | ongoing | Ongoing
Strategy #7: Policy Development | [5 empty] | 25%
2.7.1 | Grant Reporting Policy | Chief |  |  |  | 0%
2.7.2 | SAG Approval | SAG and Chief |  |  |  | 0%
2.7.3 | Grant Monitoring Policy | Chief |  |  |  | 0%
2.7.4 | SAG Approval | SAG and Chief |  |  |  | 100% |  | Grant Monitoring Draft reviewed and approved by SAG - will go through DCFS process
Note: Compliance Report Includes - goes with strategy #6.
1) Completed spreadsheet provided by the Feds outlining percentages of identified violations
2) Comprehensive Compliance Universe document - includes the number of survey's sent/received and the facilities
visited in person. There must be a 3 year history of facilities visited in person.
3) Completed DMC Report + Several Reports download from the federal RRI platform
4) State's DMC plan for reduction of DMC
5) Compliance Manual - State Policy outlining entire state compliance system
6) Compliance Plan - Specific details about staff responsibilities
7) Copies of Survey's used
8) Specific Report for Jail Removal inlcuding a list of violations
9) Specific Report for DSO including a list of violations. This also inlcudes the use of valid court orders.
10) Specific report on Sight/Sound Separation violations
11) List of Nevada Defintions for the JJ System
12) Copy of Executive order or state authority to monitor facilities
12) Copy of statute or authority on specific training requirements for staff who perform direct services on youth in secure
facilities - epecially if a facility houses both adults and juveniles.
13) Statue or authority for the use of a valid court order
14) Certification document signed by the DCFS administrator
Note: Formula Grant Application and Attachments - goes with strategy #2.
1) Grant Abstract - no more than 400 words
2) Grant Application - max 40 pages
3) Executive Order identifying the existance of a State Advisory Group - must be between 12 - 33 members and meet specific requirements
4) Appendix A - Performance Measures by Program Area
5) Appendix B - State's idnetified formula grant programs out of the 32 available programs
6) Appendix C - Waiver for pass through for sub grants - not needed for NV
7) Appendix D - State Advisory Group Roster with email addresses, appointment dates, city of residence, and area of need the person fills on the SAG
8) Appendix E - Rural Removal Exception for adult jails that are in rural areas
9) Appendix F - Formula Grant Budget and Narrative
10) Appendix G - Verification that the state submitted the required compliance report (above) by the due date.
11) Appendix H - RRI Federal Platform Analysis and Tracking Sheet
12) Appendix I - A list of the 28 program assurances - state must identify document and page number where each assurance is addressed.
13) Appendix J - Contact information for state staff associated with the JJDPA/Formula Grant from administrator to fiscal staff
14) Appendix K - Training Certification - must be signed by DCFS Administrator
15) Appendix L - Compliance Report Certification - must be signed by DCFS Administrator
16) Appendix M - Compliance Plan - System in Place - must be signed by DCFS Administrator
17) Nevada State Advisory Group Recommendations Documents
18) Fanancial Capability Document
Note: Annual Governor's Report - goes with strategy #4.
1) Narrative
2) Appendix A - State Advisory Group Roster
3) Appendix B - State Advisory Group Analysis
4) Appendix C - Grant Allocations to Nevada - JJ Grants
5) Appendix D - Formula Sub Grantees + Performance Data/Measures
6) Appendix E - Community Corrections Partnership Block Grant Allocations + Performance Data
7) Appendix F - State and County Statisical Crime Data
8) Appendix G - SB 107 Room Confinement Data

## DCFS Plan
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Develop Implementation Team
Strategy #1: Select Members From Parole/Program/Facility | [5 empty] | 100%
1.1.1 | Membership | Deputy | 2017-07-01 | 2017-10-01 | 2017-10-01 | 100% |  | Team Selected
Strategy #2: Implementation Team Work | [5 empty] | 100%
1.2.1 | Create Sub Committees | Deputy | 2017-07-01 | 2017-10-01 | 2017-10-01 | 100% |  | Committee Selected
1.2.2 | Assign projects/tasks to sub committee | Committee Chair | 2018-01-16 | 2018-01-22 | 2018-01-22 | 100% |  | Subcommittees: Parole and Facilities
1.2.3 | Schedule ongoing meetings for implementation team | CIT | 2018-01-16 | 2018-01-22 | 2018-01-22 | 100% |  | Scheduled bi-weekly
Goal #2: Agency Communication Plan
Strategy #1: Determine Messaging | [5 empty] | 68.75%
2.1.1 | What will be communicated | CIT | 2018-01-16 | 2018-04-09 | 2018-04-09 | 100% |  | Implementation Guide and PP.
2.1.2 | Send implementation guides/powerpoint on implementaion changes | Sharon Anderson | 2018-01-16 | ongoing |  | 75% |  | Updated to include NRS language
2.1.3 | Convene a meeting with line staff in facilities, parole and programs office to share information on DCFS new policies in changes | Sharon Anderson | 2018-01-16 | ongoing |  | 50% |  | in progress
2.1.4 | Establish a method for follow up and ongoing communication | Sharon Anderson/John Munoz | 2018-01-16 | ongoing |  | 50% |  | in progress
Strategy #2: Determine Sender and platform | [5 empty] | 100%
2.2.1 | Who will be the primary messenger | CIT/ Sharon Anderson | 2018-01-16 | 2018-04-10 |  | 100% |  | DCFS Staff
2.2.2 | Messenger to deliver in person, 'road show' | CIT/ Shason Anderson | 2018-07-01 | ongoing |  | 100% |  | DCFS Staff
Strategy #3: DCFS Internal Communication Plan | [5 empty] | 92.86%
2.3.1 | Communication with Superintendents, Chief of Parole and Chief of Programs Office | Sharon Anderson | 2018-01-16 | 2018-07-01 |  | 100% |  | via email with follow up meetings with minutes - communication, ongoing
2.3.2 | Communication with line staff in facilities, parole and programs office | Sharon Anderson | 2018-01-16 | 2018-07-01 |  | 100% |  | ongoing
2.3.3 | Communication with DCFS Deputies on changes | John Munoz | 2018-01-16 | 2018-07-01 |  | 50% |  | in progress
2.3.4 | Include progress updates on required changes | Sharon Anderson | 2018-01-16 | 2018-07-01 |  | 100% |  | ongoing
2.3.5 | Outline specific steps/changes that each group is responsible for making. | Sharon Anderson/John Munoz | 2018-01-16 | 2018-07-01 |  | 100% |  | ongoing
2.3.6 | Determine training timeline | Sharon Anderson/CIT | 2018-01-16 | 2018-04-10 |  | 100% |  | Parole will complete by 4/30/18; Facilities will complete by 5/31/18; NYTC completed 3/30/18.
2.3.7 | Determine which staff is from DCFS will be responsible for information distribution | Sharon Anderson/CIT | 2018-01-16 | 2018-04-10 |  | 100% |  | Parole and Facilities Trainers; NYTC is complete.
Goal #3 - Adoption and Implementation of New Regulations
Strategy #1: State Compliance for EBP Standards and QA Process (State) | [5 empty] | 79.17%
3.1.1 | Identify appropriate placement for this/policy or regulation | Administrator and Programs Office | 2017-12-15 | 2018-03-27 |  | 100% |  | Not witholding funds from state, implementing QA process
3.1.2 | Review currnt regulations to idenitfy appropriate placement. | Leslie Bittleson | 2017-12-15 | 2018-03-27 |  | 100%
3.1.3 | Gather and review policies or regs used by other states | Leslie Bittleson | 2017-12-15 | 2018-03-27 |  | 100%
3.1.4 | Contact other state subject matter experts for addidiontonal information and adoption | Leslie Bittleson | 2017-12-15 | 2018-03-27 |  | 100%
3.1.5 | Draft language for policy or regulation | Leslie Bittleston/ John Lum | 2017-12-15 | 2018-03-27 |  | 75% |  | Information added to NRS 62H.200 | Draft is being reviewed and edited internally
3.1.6 | Approval of JJOC | JJOC | 12/15/2017 |  |  | 0%
Strategy #2: Ability to withhold funding for non-compliance of EB Standards (County) | [5 empty] | 79.17%
3.2.1 | Identify appropriate placement for this/policy or regulation | Administrator and Programs Office | 2017-12-15 | 2018-04-10 |  | 100% |  | NRS 62 H will include language/ recommendation
3.2.2 | Review currnt regulations to idenitfy appropriate placement. | Leslie Bittleson | 2017-12-15 | 2018-04-10 |  | 100%
3.2.3 | Gather and review policies or regs used by other states | Leslie Bittleson | 2017-12-15 | 2018-04-10 |  | 100%
3.2.4 | Contact other state subject matter experts for addidiontonal information and adoption | Leslie Bittleson | 2017-12-15 | 2018-04-10 |  | 100%
3.2.5 | Draft language for policy or regulation | Leslie Bittleston/ John Lum | 2017-12-15 | 2018-04-11 |  | 75% |  | Draft is being reviewed and edited internally
3.2.6 | Approval of JJOC | JJOC | 2017-12-15 |  |  | 0%
Strategy #3: Review and Revise NRS 62H (DCFS Policy) | [5 empty] | 52.5%
3.3.1 | Review for appropriate language | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75% |  | NRS 62H-025 is in draft and review with John and John. | Leslie is the primary.
3.3.2 | Review for appropriate crimes | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.3.3 | Review for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.3.4 | Add language for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.3.5 | Draft updated version for review by JJOC | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-07-01 |  | 75% |  | Draft is being reviewed and edited internally
3.3.6 | Determine process for adopting new regulation | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-07-01 |  | 75%
3.3.7 | Policy Development | Leslie Bittleson | 2018-01-16 | 2018-04-10 |  | 75% |  | Draft is being reviewed and edited internally
3.3.8 | Policy Review | Leslie Bittleson | 2018-01-16 | 2018-07-01 |  | 0%
3.3.9 | Policy Approval | CIT | 2018-01-16 | 2018-07-01 |  | 0%
3.3.10 | Approval of JJOC | JJOC | 2018-01-16 |  |  | 0%
Strategy #4: Review and Revise NAC 62H (Policy DCFS) | [5 empty] | 52.5%
3.4.1 | Review for appropriate language | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.4.2 | Review for appropriate crimes | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.4.3 | Review for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.4.4 | Add language for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.4.5 | Draft updated version for review by JJOC | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-04-06 |  | 75%
3.4.6 | Determine process for adopting new regulation | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-07-01 |  | 75%
3.4.7 | Policy Development | Leslie Bittleson | 2018-01-16 | 2018-04-10 |  | 75% |  | Will be combined with NRS 62H
3.4.8 | Policy Review | Leslie Bittleson | 2018-01-16 | 2018-07-01 |  | 0%
3.4.9 | Policy Approval |  | 2018-01-16 | 2018-07-01 |  | 0%
3.4.10 | Approval of JJOC | JJOC | 2018-01-16 |  |  | 0%
Goal #4 - Policy Development (Cross Reference with JJOC Tab)
Strategy #1: Violations of Parole and Revocations (Supervision Policy) | [5 empty] | 51.92%
4.1.1 | Policy Development - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 | 2018-04-06 |  | 100% |  | Jody, Kathryn, Dolly (lead) Linda Tompkins; Draft done 4/6/18
4.1.2 | Policy Review - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 100%
4.1.3 | Policy Approval - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 0%
4.1.4 | SOP Development - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 | 2018-04-06 |  | 75% |  | John Lum/ Sharon Anderson - provide SOP for policy development
4.1.5 | SOP Approval - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 0%
4.1.6 | Policy Development - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 | 2018-04-06 |  | 100%
4.1.7 | Policy Review - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 100%
4.1.8 | Policy Approval - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 0%
4.1.9 | SOP Development - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 | 2018-04-06 |  | 75%
4.1.10 | SOP Approval - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 0%
4.1.11 | JJOC Review of Policies | Parole Subcommittee | 2018-01-25 |  |  | 100%
4.1.12 | JJOC Review of SOP's | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.13 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #2: Placement of Youth Committed to DCFS/ Admission Determination Procedure | [5 empty] | 50%
4.2.1 | Policy Development | Parole Subcommittee | 2018-01-25 | 2018-04-04 |  | 100% |  | Draft out 4/4/18
4.2.2 | Policy Review | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 100%
4.2.3 | Policy Approval | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 0%
4.2.4 | SOP Development | Parole Subcommittee | 2018-01-25 | 2018-04-04 |  | 75%
4.2.5 | SOP Approval | Parole Subcommittee | 2018-01-25 | 2018-07-01 |  | 0%
4.2.6 | JJOC Review of Policies | CIT | 2018-01-25 |  |  | 100%
4.2.7 | JJOC Review of SOP | CIT | 2018-01-25 |  |  | 0%
4.2.8 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #3: Family Engagement Plan | [5 empty] | 45%
4.3.1 | Review current SOP/policy - Parole & Facilities | Bruce Burgess | 2018-01-25 | 2018-02-06 |  | 100% |  | Reviewed areas already in place; ongoing.
4.3.2 | Compile information - Parole & Facilities | Bruce Burgess | 2018-01-25 | 2018-02-06 |  | 100% |  | Ongoing
4.3.3 | Policy Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees; Kathryn Roose | 2018-01-25 | 2018-04-06 |  | 75%
4.3.4 | Policy Review - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 75% |  | Draft is being reviewed and edited internally
4.3.5 | Policy Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.3.6 | SOP Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 75%
4.3.7 | SOP Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.3.8 | JJOC Review of Procedures | CIT | 2018-01-25 |  |  | 0%
4.3.9 | JJOC Review of SOP | CIT | 2018-01-25 |  |  | 0%
4.3.10 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #4: Court Findings Prior to Commitment (Admissions Policy) | [5 empty] | 60%
4.4.1 | Review current SOP/policy - Parole & Facilities | DCFS Parole & Facilities Subcommittees; Dave Laity | 2018-01-25 | 2018-04-06 |  | 100%
4.4.2 | Compile information - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100%
4.4.3 | Policy Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100% |  | Draft done 4/6/18
4.4.4 | Policy Review - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 100%
4.4.5 | Policy Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.4.6 | SOP Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 75% |  | Draft done 4/6/18
4.4.7 | SOP Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.4.8 | JJOC Review of Procedures | CIT | 2018-01-25 |  |  | 100%
4.4.9 | JJOC Review of SOP | CIT | 2018-01-25 |  |  | 0%
4.4.10 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #5: Individual Case Plan and Discharge Planning/Re-Entry | [5 empty] | 54.17%
4.5.1 | Review tools (YLS and MASY2) to help identify the domains | Facilities Subcommittee | 2018-01-25 | 2018-02-06 |  | 100%
4.5.2 | Review current and other tools used for Case Plan | Facilities Subcommittee | 2018-01-25 | 2018-02-06 |  | 100%
4.5.4 | Coordinate with Resource Center for EBP (discharge/re-entry) | CIT | 2018-01-25 | TBD |  | 0% |  | TBD
4.5.5 | Review current SOP/policy - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100% |  | ongoing
4.5.6 | Compile information - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100% |  | ongoing
4.5.7 | Policy Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 75% |  | Draft done 4/6/18
4.5.8 | Policy Review - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 75% |  | Draft is being reviewed and edited internally
4.5.9 | Policy Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.5.10 | SOP Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 75% |  | Draft done 4/6/18
4.5.11 | SOP Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.5.12 | JJOC Review of Procedures | CIT | 2018-01-25 |  |  | 0%
4.5.13 | JJOC Review of SOP | CIT | 2018-01-25
4.5.14 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #6: Out of State (OOS) Placement of Child | [5 empty] | 35%
4.6.1 | Policy Development | John Lum | 2018-01-25 | 2018-04-06 |  | 75%
4.6.2 | Policy Review | CIT | 2018-01-25 | 2018-07-01 |  | 75% |  | Draft is being reviewed and edited internally
4.6.3 | Policy Approval | CIT | 2018-01-25 | 2018-07-01 |  | 0%
4.6.4 | JJOC Review | CIT | 2018-01-25 |  |  | 0%
4.6.5 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #7: Release of Information/Information Sharing | [5 empty] | 87.5%
4.7.1 | Development of MOU | Leslie Bittleston | 2018-01-25 | 2018-07-01 |  | 100% |  | Completed if needed.
4.7.2 | Policy Development | Facilities Subcommittee; John Lum | 2018-01-25 | 2018-07-01 |  | 100% |  | New policy dated 7/1/18 is complete. Still need SOP's.
4.7.3 | Policy Review | Facilities Subcommittee | 2018-01-25 | 2018-07-01 |  | 100%
4.7.4 | Policy Approval | Facilities Subcommittee | 2018-01-25 | 2018-07-01 |  | 100%
4.7.5 | JJOC Review | CIT | 2018-01-25 |  |  | 100%
4.7.6 | Statewide Training | CIT | 2018-01-25 |  |  | 25%
Strategy #8: System Information Requirements (Data Collection Activities) | [5 empty] | 32.5%
4.8.1 | Review current SOP/policy - Parole & Facilities | Leslie Bittleston | 2018-01-25 | 2018-07-01 |  | 75%
4.8.2 | Compile information - Parole & Facilities | Leslie Bittleston | 2018-01-25 | 2018-07-01 |  | 75%
4.8.3 | Policy Development - Parole & Facilities | Leslie Bittleston | 2018-01-25 | 2018-07-01 |  | 75%
4.8.4 | Policy Review - Parole & Facilities |  | 2018-01-25 | 2018-07-01 |  | 75% |  | Draft is being reviewed and edited internally
4.8.5 | Policy Approval - Parole & Facilities |  | 2018-01-25 | 2018-07-01 |  | 0%
4.8.6 | SOP Development - Parole & Facilities | Leslie Bittleston | 2018-01-25 | 2018-07-01 |  | 0%
4.8.7 | SOP Approval - Parole & Facilities |  | 2018-01-25 | 2018-07-01 |  | 0%
4.8.8 | JJOC Review of Procedures | CIT | 2018-01-25 |  |  | 0%
4.8.9 | JJOC Review of SOP | CIT | 2018-01-25 |  |  | 0%
4.8.10 | Statewide Training | CIT | 2018-01-25 |  |  | 25% |  | Pending policy approval.
Strategy #9: Length of Stay | [5 empty] | 67.5%
4.9.1 | Review current SOP/policy - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100% |  | ongoing as needed
4.9.2 | Review current Matrix (discharge/re-entry) | Bruce Burgess | 2018-01-25 | 2018-02-06 |  | 100% |  | ongoing as needed
4.9.3 | Compile information - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100% |  | ongoing as needed
4.9.4 | Policy Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 100% |  | Draft done 4/6/18
4.9.5 | Policy Review - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 100%
4.9.6 | Policy Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.9.7 | SOP Development - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-04-06 |  | 75% |  | Draft done 4/6/18
4.9.8 | SOP Approval - Parole & Facilities | DCFS Parole & Facilities Subcommittees | 2018-01-25 | 2018-07-01 |  | 0%
4.9.9 | JJOC Review of Procedures | CIT | 2018-01-25 |  |  | 100%
4.9.10 | JJOC Review of SOP | CIT | 2018-01-25 |  |  | 0%
Goal #5 - Training Plan
Strategy #1: Petition by Court to Revoke Parole | [5 empty] | 50%
5.1.1 | Develop Training Plan | CIT | 2018-01-25 | Will be finalized after policy approval |  | 50%
5.1.2 | Identify who will do the training | CIT | 2018-01-25 |  |  | 50%
5.1.3 | Identify who needs the training | CIT | 2018-01-25 |  |  | 50%
5.1.4 | Parole Training | CIT | 2018-01-25 |  |  | 50%
5.1.5 | Facilities Training | CIT | 2018-01-25 |  |  | 50%
Strategy #2: Newly created policy training by DCFS and JJOC | [5 empty] | 50%
5.2.1 | Develop Training Plan | CIT | 2018-01-25 | Will be finalized after policy approval |  | 50% |  | Tentative training plan, pending policy approval.