## JJOC
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Establish Standard Procedures for Measuring Outcomes
Strategy #1: Identify Outcomes measures | [5 empty] | 0%
1.1.1 | Establish outcomes measures for statewide system improvement measures | JJOC | 2017-12-15 | 2018-06-30 |  | 0%
Goal #2 - Reporting Requirements of JJOC and DCFS
Strategy #1: Annual LCB Compliance Report | [5 empty] | 92.5%
2.1.1 | Create a template | JJOC | 2017-12-15 | 2018-01-31 |  | 90%
2.1.2 | Establish ownership of this report | JJOC | 2017-12-15 |  |  | 100%
2.1.3 | Submit completed report | JJOC | 2017-12-15 | 2018-01-31 |  | 90% |  | Under review by Commission Chairs
2.1.4 | Submit final report to Governor's office | JJOC | 2017-12-15 | 2018-01-31 |  | 90% |  | Under review by Commission Chairs
Strategy #2: Annual Report to the Governor | [5 empty] | 0%
2.2.1 | Create a template | JJOC |  | 2018-07-01 |  | 0%
2.2.2 | Establish ownership of this report | JJOC |  | 2018-07-01 |  | 0%
2.2.3 | Submit completed report | JJOC |  | 2018-07-01 |  | 0%
2.2.4 | Submit final report to LCB | JJOC |  | 2018-07-01 |  | 0%
Goal #3 - Annual Quality Assurance Review
Strategy #1: Quality Assurance Tool | [5 empty] | 11.67%
3.1.1 | JJOC must select QA Tool | Kelly Wooldridge | 2017-12-05 |  |  | 35% |  | Kelly will provide information at next JJOC on tools being researched
3.1.2 | JJOC to receive training on use of tool | JJOC |  |  |  | 0%
3.1.3 | Determine who will be responsible for conducting review | DCFS QA Contractor |  |  |  | 0%
Strategy #2: Utilization of Tool and Review Process | [5 empty] | 0%
3.2.1 | Determine timeline of each facility review | DCFS QA Contractor |  |  |  | 0%
3.2.2 | Develop procedures for use of QA Review Tool | DCFS QA Contractor |  |  |  | 0%
3.2.3 | Develop procedures for Quality Improvement Plan | DCFS QA Contractor |  |  |  | 0%
3.2.4 | Develop procedures for JJOC to review QA Reviews from facilities | DCFS QA Contractor |  |  |  | 0%
Goal #4 - Adoption and Implementation of New Regulations
Strategy #1: Ability to withhold funding for non-compliance of EB Standards | [5 empty] | 0%
4.1.1 | Identify appropriate placement for this/policy or regulation | JJOC |  |  |  | 0% |  | Oversight to remain with funding source
4.1.2 | Draft language for policy or regulation | JJOC |  |  |  | 0%
4.1.3 | Policy review and approval by JJOC | JJOC |  |  |  | 0%
Strategy #2: Review and Revise NRS 62H | [5 empty] | 0%
4.2.1 | Review for appropriate language | JJOC |  |  |  | 0%
4.2.2 | Review for appropriate crimes | JJOC |  |  |  | 0%
4.2.3 | Review for reporting requirements | JJOC |  |  |  | 0%
4.2.4 | Add language for reporting requirements | JJOC |  |  |  | 0%
4.2.5 | Draft updated version for review by JJOC | JJOC |  |  |  | 0%
4.2.6 | Determine process for adopting new regulation | JJOC |  |  |  | 0%
Strategy #3: Review and Revise NAC 62H | [5 empty] | 0%
4.3.1 | Review for appropriate language | JJOC |  |  |  | 0%
4.3.2 | Review for appropriate crimes | JJOC |  |  |  | 0%
4.3.3 | Review for reporting requirements | JJOC |  |  |  | 0%
4.3.4 | Add language for reporting requirements | JJOC |  |  |  | 0%
4.3.5 | Draft updated version for review by JJOC | JJOC |  |  |  | 0%
4.3.6 | Determine process for adopting new regulation | JJOC |  |  |  | 0%
Goal #5 - Development of By-Laws and Participation Requirements | [5 empty] | 0%
5.1 | Develop By-Laws for JJOC | Joey, Kelly, Alexis | 2018-01-12 | 2018-02-28 |  | 0%
5.2 | Determine participation requirements | JJOC |  |  |  | 0%
5.3 | Review By-Laws | JJOC |  |  |  | 0%
5.4 | Approve By-Laws | JJOC |  |  |  | 0%
Goal #6: Policy Development (Cross Reference DCFS Tab)
Strategy #1: Violations of Parole and Revication | [5 empty] | 0%
6.1.1 | JJOC Review of Policy |  |  |  |  | 0%
6.1.2 | JJOC Review of SOP |  |  |  |  | 0%
0%
Strategy #2: Placement of Youth Committed to DCFS/ Admission Determination Procedure | [5 empty] | 0%
6.2.1 | JJOC Review of Policy |  |  |  |  | 0%
6.2.2 | JJOC Review of SOP |  |  |  |  | 0%
6.2.3 | [5 empty] | 0%
Strategy #3: Family Engagement Plan | [5 empty] | 0%
6.3.1 | JJOC Review of Policy |  |  |  |  | 0%
6.3.2 | JJOC Review of SOP |  |  |  |  | 0%
6.3.3 | [5 empty] | 0%
Strategy # 4: Court Finidings Prior to Committment | [5 empty] | 0%
6.4.1 | JJOC Review of Policy |  |  |  |  | 0%
6.4.2 | JJOC Review of SOP |  |  |  |  | 0%
6.4.3 | [5 empty] | 0%
Strategy #5: Individual Case Plan | [5 empty] | 0%
6.5.1 | JJOC Review of Policy |  |  |  |  | 0%
6.5.2 | JJOC Review of SOP |  |  |  |  | 0%
6.5.3 | [5 empty] | 0%
Strategy #6: Out of State (OOS) Placement of Children | [5 empty] | 0%
6.6.1 | JJOC Review of Policy |  |  |  |  | 0%
6.6.2 | JJOC Review of SOP |  |  |  |  | 0%
6.6.3 | [5 empty] | 0%
Strategy #7: Discharge Planning/ Re-Entry | [5 empty] | 0%
6.7.1 | JJOC Review of Policy |  |  |  |  | 0%
6.7.2 | JJOC Review of SOP |  |  |  |  | 0%
6.7.3 | [5 empty] | 0%
Strategy #8:Release of Information/ Information Sharing | [5 empty] | 0%
6.8.1 | JJOC Review of Policy |  |  |  |  | 0%
6.8.2 | JJOC Review of SOP |  |  |  |  | 0%
6.8.3
Strategy #9: System Information Requirements (Data Collection Activities) | [5 empty] | 0%
6.9.1 | JJOC Review of Policy |  |  |  |  | 0%
6.9.2 | JJOC Review of SOP |  |  |  |  | 0%
6.9.3

## Strategic Plan
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Evidence Based Practices
Strategy #1: Vendor Procurement for Resource Center | [5 empty] | 70%
1.1.1 | Develop RFP to select a vendor for EBP Resource Center | DCFS | 2017-09-28 | 2017-11-16 | 2017-11-16 | 100% |  | Selection Made | 3 vendor applications received
1.1.2 | Evaluation and selection of Vendor | State Purchasing | 2017-11-16 | 2017-11-16 | 2017-11-16 | 100% |  | Selection Made | Evaluation committee of 4; selection made
1.1.3 | Contract development | State Purchasing | 2017-11-16 | 2017-12-15 |  | 100% |  |  | Routing contract for signatures
1.1.4 | BOE Review of Contract | State Purchasing | 2017-11-16 | 2017-02-13 |  | 50%
1.1.5 | Establish Invoice Process | Brian Dahlberg | 2018-01-12 | 2018-02-13 |  | 0%
Strategy #2: Selection of EBP Models by Vendor | [5 empty] | 0%
1.2.1 | Vendor to identify appropriate EBP's for state-wide utilization | Vendor | 2017-01-12 |  |  | 0%
1.2.2 | Determine uniform standards that EBP must follow | Sub committee | 2017-01-12 |  |  | 0%
1.2.3 | Staffing requirements | Vendor | 2017-01-12 |  |  | 0%
1.2.4 | Quality Insurance Protocols | Vendor | 2017-01-12 |  |  | 0%
Strategy #3: Develop Policies for Utilization of EBP's | [5 empty] | 0%
1.3.1 | Identify what entity owns the Policy | Vendor |  |  |  | 0%
1.3.2 | Identify where policy will be available | Vendor |  |  |  | 0%
1.3.3 | Determine timeline for policy development | JJOC |  |  |  | 0%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
1.3.5 | Date of policy implementation | JJOC |  |  |  | 0%
Strategy #4: Development of Procedures for Utilization of EBP's | [5 empty] | 0%
1.4.1 | Identify what entity owns the Procedure | Sub Committee |  |  |  | 0%
1.4.2 | Identify where procedure will be available | Sub Committee |  |  |  | 0%
1.4.3 | Determine timeline for procedure development | Sub Committee |  |  |  | 0%
1.4.4 | Determine appropriate review process and approval of procedures | JJOC |  |  |  | 0%
1.4.5 | Date of procedure implementation | JJOC |  |  |  | 0%
Goal #2: Training Program to Enhance EBP's
Strategy #1: Vendor to Develop Training Plan | [5 empty] | 0%
2.1.1 | Training Plan approved by subcommittee | Vendor |  |  |  | 0%
2.1.2 | Training Plan approved by JJOC | JJOC |  |  |  | 0%
Strategy #2: Implementation of Training | [5 empty] | 0%
2.2.1 | Identify who needs training | Vendor & JJOC |  |  |  | 0%
2.2.2 | Develop timeline for training | Vendor & JJOC |  |  |  | 0%
2.2.3 | Identification of ongoing training needs | Vendor & JJOC |  |  |  | 0%
Goal #3: Reporting Requirements for EBP's
Strategy #1: Reports to JJOC | [5 empty] | 0%
3.1.1 | Determine who has oversight and responsibility for report development | Sub Committee |  |  |  | 0%
3.1.2 | Develop Policy specific to reporting requirements | Sub Committee |  |  |  | 0%
3.1.3 | Develop Procedure for frequency of reporting | Sub Committee |  |  |  | 0%
Strategy #2: Quality Assurance | [5 empty] | 0%
3.2.1 | Develop Policies for Quality Improvement Plan for reporting | Vendor and Sub Committee |  |  |  | 0%
3.2.2 | Develop Procedures for Quality Improvement plan for reporting including Corrective Action Plan | Vendor and Sub Committee |  |  |  | 0%
3.2.3 | Select a QA Tool for review | Vendor |  |  |  | 0%
3.2.4 | Training on QA Tool selected | Vendor |  |  |  | 0%
Goal #4: Development and Revisions to 5 Year Strategic Plan
Strategy #1: Authority and Revisions | [5 empty] | 0%
4.1.1 | Determine who has oversight and responsibility for development and revisions to Strategic Plan | JJOC |  |  |  | 0%
4.1.2 | Determine where will strategic plan be published | JJOC |  |  |  | 0%
4.1.3 | Develop Template for 5 yr. Strategic Plan | DCFS
4.1.4 | Develop Template for Annual Report to the 5 yr. Strategic Plan | DCFS |  |  |  | 0%
Strategy #2: Information to be included in 5 Year Plan | [5 empty] | 0%
4.2.1 | Develop specific goals for 5 year plan with measurable benchmarks | Sub Committee |  |  |  | 0%
4.2.2 | Document individual subcommittees, their functions and goals | Sub Committee |  |  |  | 0%
4.2.3 | Develop timeline of implementation with benchmarks | Sub Committee |  |  |  | 0%
4.2.4 | Document reporting requirements | Sub Committee |  |  |  | 0%
4.2.5 | Address Family Engagement Plan | Sub Committee |  |  |  | 0%
4.2.6 | Address Court Findings Prior to Commitment | Sub Committee |  |  |  | 0%
4.2.7 | Address Individual Case Plan | Sub Committee |  |  |  | 0%
4.2.8 | Address Placement of Child | Sub Committee |  |  |  | 0%
4.2.9 | Address Out of State (OOS) Placement of Child | Sub Committee |  |  |  | 0%
4.2.10 | Address Release of Information/Information Sharing | Sub Committee |  |  |  | 0%
4.2.11 | Address System Information Requirements (Data Collection Activities) | Sub Committee |  |  |  | 0%
Strategy #3: Information to be included in Annual Report to Strategic Plan | [5 empty] | 0%
4.3.1 | Document individual subcommittee outcomes | Sub Committee |  |  |  | 0%
4.3.2 | Document completion dates of tasks | Sub Committee |  |  |  | 0%
4.3.3 | Document next steps | Sub Committee |  |  |  | 0%
Strategy #4: Review Process of Strategic Plan | [5 empty] | 0%
4.4.1 | Review by Subcommittee | Sub Committee |  |  |  | 0%
4.4.2 | Review by JJOC | JJOC |  |  |  | 0%

## Risk Asmnt and MH Screen
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Risk Assessment Tool
Strategy #1: Select Risk Assessment Tool | [5 empty] | 100%
1.1.1 | Review available risk assessments | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100% |  | Committee voted to select the YLS as the Risk and Needs Assessment tool on 12/06/2017.Pending JJOC Approval | JJOC voted and approved the use of the YLS.
1.1.2 | Select agreed upon risk assessment tool | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100%
Strategy #2: Training Risk Assessment Tool State-Wide | [5 empty] | 0%
1.2.1 | Identify who needs training | Vendor and JJOC |  |  |  | 0%
1.2.2 | Develop timeline for training | JJOC |  |  |  | 0%
1.2.3 | What entity will own training for Train the Trainer | JJOC |  |  |  | 0%
Strategy #3: Develop State-Wide Policy for Risk Assessment | [5 empty] | 0%
1.3.1 | Identify what entity owns the Policy | Sub Committee |  |  |  | 0%
1.3.2 | Identify where policy will be available | Sub Committee |  |  |  | 0%
1.3.3 | Determine timeline for policy development | Sub Committee |  |  |  | 0%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
1.3.5 | Determine frequency of Risk Assessment | Vendor |  |  |  | 0%
1.3.6 | Date of policy implementation | DCFS |  |  |  | 0%
Strategy #4: Develop Quality Improvement Process for Risk Assessment Tool | [5 empty] | 0%
1.4.1 | Determine who has oversight of Quality Improvement actions | JJOC |  |  |  | 0%
1.4.2 | Develop Quality Improvement guidelines including acceptable standards | Vendor |  |  |  | 0%
1.4.3 | Develop Quality Improve Process | Vendor & Sub Committee |  |  |  | 0%
1.4.4 | Conduct Quality Reviews | DCFS Contractor |  |  |  | 0%
1.4.5 | Determine QA reporting back to JJOC | DCFS and Sub Committee |  |  |  | 0%
Goal #2 - Mental Health Screening Tool
Strategy #1: Select Mental Health Screening Tool | [5 empty] | 100%
2.1.1 | Review available risk assessments | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100% |  | Committee voted to select the MAYSI II as the statewide Mental Health Screening tool on 12/06/2017. Pending JJOC Approval | JJOC voted and approved the use of the MAYSI II
2.1.2 | Select agreed upon risk assessment tool | Sub Committee | 2017-11-30 | 2017-12-06 | 2015-12-15 | 100%
Strategy #2: Training Mental Health Screen Tool State-Wide | [5 empty] | 0%
2.2.1 | Identify who needs training | Vendor and JJOC |  |  |  | 0% |  | Note: The MAYSI II vendor may not offer training, what is plan B?
2.2.2 | Develop timeline for training | JJOC |  |  |  | 0%
2.2.3 | What entity will own training for Train the Trainer | JJOC |  |  |  | 0%
Strategy #3: Develop State-Wide Policy for Mental Health Screen | [5 empty] | 0%
2.3.1 | Identify what entity owns the Policy | Sub Committee |  |  |  | 0%
2.3.2 | Identify where policy will be available | Sub Committee |  |  |  | 0%
2.3.3 | Determine timeline for policy development | Sub Committee |  |  |  | 0%
2.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
2.3.5 | Determine frequency of Mental Health Screen | Vendor |  |  |  | 0%
2.3.6 | Date of policy implementation | DCFS |  |  |  | 0%
Strategy #4: Develop Quality Improvement Process for Mental Health Screen | [5 empty] | 0%
2.4.1 | Determine who has oversight of Quality Improvement actions | JJOC |  |  |  | 0%
2.4.2 | Develop Quality Improvement guidelines including acceptable standards | Vendor |  |  |  | 0%
2.4.3 | Develop Quality Improvement Process | Vendor & Sub Committee |  |  |  | 0%
2.4.4 | Conduct Quality Reviews | DCFS Contractor |  |  |  | 0%
2.4.5 | Determine QA reporting back to JJOC | DCFS and Sub Committee |  |  |  | 0%
Goal #3: Caseload PRO Inclusion | [5 empty] | 0%
3.1 | Include the Selected Risk Assessment Tool into Caseload Pro | JJOC/Counties/DCFS |  |  |  | 0%
3.2 | Include the Selected Mental Health Screening Tool into Caseload Pro | JJOC/Counties/DCFS |  |  |  | 0%
3.3 | Determine cost of inclusion and who will fund this | JJOC/Counties/DCFS |  |  |  | 0%
3.4 | Identify reporting requirements for both tools from Caseload PRO | JJOC/Counties/DCFS |  |  |  | 0%

## Data and Perf Measure
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
Develop Performance Measures for Recidivism | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Recidivism
Strategy #1: Recommend Definition for JJOC Adoption | [5 empty] | 18%
1.1.1 | Review Past definitions by Supreme Court Commission | Sub Committee |  |  |  | 90% |  | Reviewed by JJOC | Further discussion needed based on JJOC meeting.
1.1.2 | Determine if revision is needed, if yes, revise definition | Sub Committee |  | 2018-03-31 |  | 0%
1.1.3 | Sub Committee Selection or Recommendation to JJOC | Sub Committee |  |  |  | 0%
1.1.4 | JJOC adoption of definition | JJOC and DCFS |  |  |  | 0%
1.1.5 | Inclusion of Definition in Regulation | JJOC and DCFS |  |  |  | 0%
Strategy #2: Develop Performance Measures for Recidivism | [5 empty] | 0%
1.2.1 | Review current accessible data to determine measures | Sub Committee |  |  |  | 0%
1.2.2 | Research what other states are utilizing | Sub Committee |  |  |  | 0%
1.2.3 | Develop reporting mechanism | Sub Committee |  |  |  | 0%
1.2.4 | Determine frequency of reporting | Sub Committee |  |  |  | 0%
1.2.5 | Determine who has oversight of data | JJOC |  |  |  | 0%
1.2.6 | Develop consistent dashboard for reporting purposes | JJOC/Counties/DCFS/Caseload Pro |  |  |  | 0%
Strategy #3: Develop Policies for Recidivism | [5 empty] | 0%
1.3.1 | Identify what entity owns the Policy | Sub Committee or JJOC |  |  |  | 0%
1.3.2 | Identify where policy will be available | Sub Committee or JJOC |  |  |  | 0%
1.3.3 | Determine timeline for policy development | Sub Committee or JJOC |  |  |  | 0%
1.3.4 | Determine appropriate review process and approval of policy | JJOC |  |  |  | 0%
1.3.5 | Date of policy implementation | DCFS |  |  |  | 0%
Goal #2: Creation of a Set of Performance Measures
Strategy #1: Points of Measurement | [5 empty] | 0%
2.1.1 | Determine requirement information for state-wide data | Sub Committee |  |  |  | 0%
2.1.2 | Develop required performance measures | Sub Committee |  |  |  | 0%
2.1.3 | Determine who has oversight to requirements | JJOC |  |  |  | 0%
2.1.4 | Determine if performance measures need to be adopted into regulation | JJOC |  |  |  | 0%
Strategy #2: Performance Measures Defined and Policy Development | [5 empty] | 0%
2.2.1 | Define specific measurements | Sub Committee |  |  |  | 0%
2.2.2 | Develop Policy for Performance Measures | Sub Committee |  |  |  | 0%
2.2.3 | Determine who has oversight and is responsible for Policy revisions in the future | Sub Committee |  |  |  | 0%
Goal #3: Quality Improvement Process
Strategy #1: Develop Quality Improvement Process | [5 empty] | 0%
3.1.1 | Determine timeline to validate data | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.2 | Determine what entity will be responsible for data validation | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.3 | Determine frequency validation | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.4 | Develop corrected action plan process | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%
3.1.5 | Document Quality Improvement Process | JJOC/Sub Committee and DCFS Contractor |  |  |  | 0%

## Youth
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Development of Youth Group
Strategy #1: Selection of Members | [5 empty] | 100%
1.1.1 | Determine mandated positions from AB472 | Governor's Office |  |  |  | 100%
1.1.2 | Governor appoints members | Governor's Office |  |  |  | 100%
1.1.3 | Ensure youth member positions are always filled | JJOC and Governor's Office |  |  |  | 100%
Strategy #2: Process for Continued Participation | [5 empty] | 10%
1.2.1 | Develop strategy to incentivize youth participation | Sub Committee |  |  |  | 10% |  | Ice Breaker Meeting
1.2.2 | Determine budgetary needs if a stipend is offered | JJOC |  |  |  | 10% |  | Potential gas cards
Goal #2 - Communication of Youth Voice
Strategy #1: Determine Areas to Address from Youth Perspective | [5 empty] | 2%
2.1.1 | Select sites to visit | Sub Committee |  |  |  | 10% |  | Reviewed locations
2.1.2 | Schedule site visits |  |  |  |  | 0%
2.1.3 | Develop youth focused areas for focus | Sub Committee |  |  |  | 0%
2.1.4 | Determine potential intercepts | Sub Committee |  |  |  | 0%
2.1.5 | Determine process how areas of focus can be revised | Sub Committee |  |  |  | 0%
Strategy #2: Determine Communication Format | [5 empty] | 0%
2.2.1 | Develop format to provide feedback to JJOC | Sub Committee |  |  |  | 0%
2.2.2 | Determine if there are other avenues and/or platforms to provide education and communication | Sub Committee |  |  |  | 0%
Goal #3 - Youth Education
Strategy #1: Determine How to Educate Community of JJ System | [5 empty] | 0%
3.1.1 | Determine message to communicate to public | Sub Committee |  |  |  | 0%
3.1.2 | Determine how to educate youth community | Sub Committee |  |  |  | 0%
3.1.3 | Determine how to educate adults on youth needs and supports | Sub Committee |  |  |  | 0%
3.1.4 | Determine education needs to law enforcement | Sub Committee |  |  |  | 0%
Strategy #2: Develop Community Partnerships | [5 empty] | 0%
3.2.1 | Determine needs of youth in the community | Sub Committee |  |  |  | 0%
3.2.2 | Develop partnerships with community agencies. | Sub Committee |  |  |  | 0%
3.2.3 | Develop partnerships for supported employment | Sub Committee |  |  |  | 0%
3.2.4 | Develop partnerships for supported educational needs | Sub Committee |  |  |  | 0%

## DCFS Plan
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Develop Implementation Team
Strategy #1: Select Members From Parole/Program/Facility | [5 empty] | 100%
1.1.1 | Membership | Deputy | 2017-07-01 | 2017-10-01 | 2017-10-01 | 100% |  | Team Selected
Strategy #2: Implementation Team Work | [5 empty] | 100%
1.2.1 | Create Sub Committees | Deputy | 2017-07-01 | 2017-10-01 | 2017-10-01 | 100% |  | Committee Selected
1.2.2 | Assign projects/tasks to sub committee | Committee Chair | 2018-01-16 |  |  | 100% |  | Subcommittees: Parole and Facilities
1.2.3 | Schedule ongoing meetings for implementation team |  | 2018-01-16 | 2018-01-22 | 2018-01-22 | 100% |  | Scheduled bi-weekly
Goal #2: Agency Communication Plan
Strategy #1: DCFS Internal Communication Plan | [5 empty] | 10%
2.1.1 | Communication with Superintendents, Chief of Parole and Chief of Programs Office | Sharon Anderson |  |  |  | 10% |  | via email with follow up meetings with minutes - communication
2.1.2 | Communication with line staff in facilities, parole and programs office | Sharon Anderson |  |  |  | 10%
2.1.3 | Communication with DCFS Deputies on changes | John Munoz |  |  |  | 10%
Strategy #2: Determine Messaging | [5 empty] | 10%
2.2.1 | What will be communicated | CIT |  |  |  | 10%
Strategy #3: Determine Sender and platform | [5 empty] | 5%
2.3.1 | Who will be the primary messenger | CIT |  |  |  | 10%
2.3.2 | Messenger to deliver in person, 'road show' | CIT |  |  |  | 0%
Goal #3 - Adoption and Implementation of New Regulations
Strategy #1: Ability to withhold funding for non-compliance of EB Standards | [5 empty] | 0%
3.1.1 | Identify appropriate placement for this/policy or regulation | Administrator and Programs Office |  |  |  | 0%
3.1.2 | Draft language for policy or regulation | Leslie Bittleston/ John Lum |  |  |  | 0%
3.1.3 | Approcal of JJOC | JJOC |  |  |  | 0%
Strategy #2: Review and Revise NRS 62H (DCFS Policy) | [5 empty] | 3.333%
3.2.1 | Review for appropriate language | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-02-16 |  | 20% |  | NRS 62H-025 is in draft and review
3.2.2 | Review for appropriate crimes | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-02-17 |  | 0%
3.2.3 | Review for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-02-18 |  | 0%
3.2.4 | Add language for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG |  |  |  | 0%
3.2.5 | Draft updated version for review by JJOC | Leslie Bittleston/John Munoz/ John Lum/ DAG |  |  |  | 0%
3.2.6 | Determine process for adopting new regulation | Leslie Bittleston/John Munoz/ John Lum/ DAG |  |  |  | 0%
Strategy #3: Review and Revise NAC 62H (Policy DCFS) | [5 empty] | 0%
3.3.1 | Review for appropriate language | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-02-16 |  | 0%
3.3.2 | Review for appropriate crimes | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-02-17 |  | 0%
3.3.3 | Review for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG | 2018-01-16 | 2018-02-18 |  | 0%
3.3.4 | Add language for reporting requirements | Leslie Bittleston/John Munoz/ John Lum/ DAG |  |  |  | 0%
3.3.5 | Draft updated version for review by JJOC | Leslie Bittleston/John Munoz/ John Lum/ DAG |  |  |  | 0%
3.3.6 | Determine process for adopting new regulation | Leslie Bittleston/John Munoz/ John Lum/ DAG |  |  |  | 0%
Goal #4 - Policy Development (Cross Reference with JJOC Tab)
Strategy #1: Violations of Parole and Revocations | [5 empty] | 1.538%
4.1.1 | Policy Development - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 | 2018-02-06 |  | 10% |  | Jody, Kathryn, Dolly (lead)
4.1.2 | Policy Review - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.3 | Policy Approval - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.4 | SOP Development - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 |  |  | 0% |  | John Lum/ Sharon Anderson - provide SOP for policy development
4.1.5 | SOP Approval - Responses to Violations and Terms of Parole | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.6 | Policy Development - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 | 2018-02-06 |  | 10%
4.1.7 | Policy Review - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.8 | Policy Approval - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.9 | SOP Development - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.10 | SOP Approval - Recommendations of Revocation | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.1.11 | JJOC Review of Policies | Parole Subcommittee |  |  |  | 0%
4.1.12 | JJOC Review of SOP's | Parole Subcommittee |  |  |  | 0%
| Statewide Training | CIT |  |  |  | 0%
Strategy #2: Placement of Youth Committed to DCFS/ Admission Determination Procedure | [5 empty] | 0%
4.2.1 | Policy Development | Parole Subcommittee |  |  |  | 0%
4.2.2 | Policy Review | Parole Subcommittee |  |  |  | 0%
4.2.3 | Policy Approval | Parole Subcommittee |  |  |  | 0%
4.2.4 | SOP Development | Parole Subcommittee |  |  |  | 0%
4.2.5 | SOP Approval | Parole Subcommittee |  |  |  | 0%
4.2.6 | JJOC Review of Policies | CIT |  |  |  | 0%
4.2.7 | JJOC Review of SOP | CIT |  |  |  | 0%
4.2.8 | Statewide Training | CIT |  |  |  | 0%
Strategy #3: Family Engagement Plan | [5 empty] | 0.6667%
4.3.1 | Review current SOP/policy - Parole | Bruce Burgess | 2018-01-25 | 2018-02-06 |  | 10%
4.3.2 | Compile information - Parole | Bruce Burgess | 2018-01-25 | 2018-02-06 |  | 0%
4.3.3 | Policy Development - Parole | DCFS Parole Subcommittee | 2018-01-25 |  |  | 0%
4.3.4 | Policy Review - Parole | Parole Subcommittee |  |  |  | 0%
4.3.5 | Policy Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.3.6 | SOP Development - Parole | Parole Subcommittee |  |  |  | 0%
4.3.7 | SOP Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.3.8 | Review current SOP/policy - Facilities | Facilities Subcommittee |  |  |  | 0%
4.3.9 | Compile information - Facilities | Facilities Subcommittee |  |  |  | 0%
4.3.10 | Policy Development - Facilities | Facilities Subcommittee |  |  |  | 0%
4.3.11 | Policy Review - Facilities | Facilities Subcommittee |  |  |  | 0%
4.3.12 | Policy Approval - Facilities | Facilities Subcommittee |  |  |  | 0%
4.3.13 | JJOC Review of Procedures | CIT |  |  |  | 0%
4.3.14 | JJOC Review of SOP | CIT |  |  |  | 0%
4.3.15 | Statewide Training | CIT |  |  |  | 0%
Strategy #4: Court Findings Prior to Commitment | [5 empty] | 0%
4.4.1 | Review current SOP/policy - Parole | Parole Subcommittee |  |  |  | 0%
4.4.2 | Compile information - Parole | Parole Subcommittee |  |  |  | 0%
4.4.3 | Policy Development - Parole | Parole Subcommittee |  |  |  | 0%
4.4.4 | Policy Review - Parole | Parole Subcommittee |  |  |  | 0%
4.4.5 | Policy Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.4.6 | SOP Development - Parole | Parole Subcommittee |  |  |  | 0%
4.4.7 | SOP Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.4.8 | Review current SOP/policy - Facilities | Facilities Subcommittee |  |  |  | 0%
4.4.9 | Compile information - Facilities | Facilities Subcommittee |  |  |  | 0%
4.4.10 | Policy Development - Facilities | Facilities Subcommittee |  |  |  | 0%
4.4.11 | Policy Review - Facilities | Facilities Subcommittee |  |  |  | 0%
4.4.12 | Policy Approval - Facilities | Facilities Subcommittee |  |  |  | 0%
4.4.13 | JJOC Review of Procedures | CIT |  |  |  | 0%
4.4.14 | JJOC Review of SOP | CIT |  |  |  | 0%
4.4.15 | Statewide Training | CIT |  |  |  | 0%
Strategy #5: Individual Case Plan | [5 empty] | 1.25%
4.5.1 | Review tools (YLS and MASY2) to help identify the domains | Facilities Subcommittee | 2018-01-25 | 2018-02-06 |  | 10% |  | Alexis will identify counties using tools & connect to group
4.5.2 | Review current and other tools used for Case Plan | Facilities Subcommittee | 2018-01-25 | 2018-02-06 |  | 10%
4.5.3 | Review current SOP/policy - Parole | Parole Subcommittee | 2018-01-25 |  |  | 0%
4.5.4 | Compile information - Parole | Parole Subcommittee |  |  |  | 0%
4.5.5 | Policy Development - Parole | Parole Subcommittee |  |  |  | 0%
4.5.6 | Policy Review - Parole | Parole Subcommittee |  |  |  | 0%
4.5.7 | Policy Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.5.8 | SOP Development - Parole | Parole Subcommittee |  |  |  | 0%
4.5.9 | SOP Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.5.10 | Review current SOP/policy - Facilities | Facilities Subcommittee |  |  |  | 0%
4.5.11 | Compile information - Facilities | Facilities Subcommittee |  |  |  | 0%
4.5.12 | Policy Development - Facilities | Facilities Subcommittee |  |  |  | 0%
4.5.13 | Policy Review - Facilities | Facilities Subcommittee |  |  |  | 0%
4.5.14 | Policy Approval - Facilities | Facilities Subcommittee |  |  |  | 0%
4.5.15 | JJOC Review of Procedures | CIT |  |  |  | 0%
4.5.16 | JJOC Review of SOP | CIT
4.5.17 | Statewide Training | CIT |  |  |  | 0%
Strategy #6: Out of State (OOS) Placement of Child | [5 empty] | 0%
4.6.1 | Policy Development | John Lum |  |  |  | 0%
4.6.2 | Policy Review |  |  |  |  | 0%
4.6.3 | Policy Approval |  |  |  |  | 0%
4.6.4 | JJOC Review |  |  |  |  | 0%
Strategy #7: Discharge Planning/Re-Entry | [5 empty] | 0.5882%
4.7.1 | Review current Matrix | Bruce Burgess | 2018-01-25 | 2018-02-06 |  | 10% |  | Bruce will distribute to group
7.7.2 | Coordinate with Resource Center for EBP | CIT |  |  |  | 0%
4.7.3 | Review current SOP/policy - Parole | Parole Subcommittee |  |  |  | 0%
4.7.2 | Compile information - Parole | Parole Subcommittee |  |  |  | 0%
7.7.3 | Policy Development - Parole | Parole Subcommittee |  |  |  | 0%
4.7.4 | Policy Review - Parole | Parole Subcommittee |  |  |  | 0%
4.7.3 | Policy Approval - Parole | Parole Subcommittee |  |  |  | 0%
7.7.4 | SOP Development - Parole | Parole Subcommittee |  |  |  | 0%
4.7.5 | SOP Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.7.4 | Review current SOP/policy - Facilities | Facilities Subcommittee |  |  |  | 0%
7.7.5 | Compile information - Facilities | Facilities Subcommittee |  |  |  | 0%
4.7.6 | Policy Development - Facilities | Facilities Subcommittee |  |  |  | 0%
4.7.5 | Policy Review - Facilities | Facilities Subcommittee |  |  |  | 0%
7.7.6 | Policy Approval - Facilities | Facilities Subcommittee |  |  |  | 0%
4.7.7 | JJOC Review of Procedures | CIT |  |  |  | 0%
4.7.6 | JJOC Review of SOP | CIT |  |  |  | 0%
7.7.7 | Statewide Training | CIT |  |  |  | 0%
Strategy #8: Release of Information/Information Sharing | [5 empty] | 23%
4.8.1 | Development of MOU | Leslie Bittleston |  |  |  | 75%
4.8.2 | Policy Development | Facilities Subcommittee |  |  |  | 20%
4.8.3 | Policy Review | Facilities Subcommittee |  |  |  | 20%
4.8.4 | Policy Approval | Facilities Subcommittee |  |  |  | 0%
4.8.5 | JJOC Review | CIT
4.8.6 | Statewide Training | CIT |  |  |  | 0%
Strategy #9: System Information Requirements (Data Collection Activities) | [5 empty] | 0%
4.9.1 | Review current SOP/policy - Parole | Parole Subcommittee |  |  |  | 0%
4.9.2 | Compile information - Parole | Parole Subcommittee |  |  |  | 0%
4.9.3 | Policy Development - Parole | Parole Subcommittee |  |  |  | 0%
4.9.4 | Policy Review - Parole | Parole Subcommittee |  |  |  | 0%
4.9.5 | Policy Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.9.6 | SOP Development - Parole | Parole Subcommittee |  |  |  | 0%
4.9.7 | SOP Approval - Parole | Parole Subcommittee |  |  |  | 0%
4.9.8 | Review current SOP/policy - Facilities | Facilities Subcommittee |  |  |  | 0%
4.9.9 | Compile information - Facilities | Facilities Subcommittee |  |  |  | 0%
4.9.10 | Policy Development - Facilities | Facilities Subcommittee |  |  |  | 0%
4.9.11 | Policy Review - Facilities | Facilities Subcommittee |  |  |  | 0%
4.9.12 | Policy Approval - Facilities | Facilities Subcommittee |  |  |  | 0%
4.9.13 | JJOC Review of Procedures | CIT |  |  |  | 0%
4.9.14 | JJOC Review of SOP | CIT |  |  |  | 0%
4.9.15 | Statewide Training | CIT |  |  |  | 0%
Goal #5 - Training Plan
Strategy #1: Petition by Court to Revoke Parole | [5 empty] | 0%
5.1.1 | Parole Training |  |  |  |  | 0%
5.1.2 | Facilities Training |  |  |  |  | 0%
Strategy #2: Newly created policy training by DCFS and JJOC | [5 empty] | 0%
5.2.1 | Develop policy |  |  |  |  | 0%