## Youth
DATA ENTRY ON THIS PAGE ONLY
Key | Indicates activity is complete
Indicates activity is on schedule, no risk factor
Indicates activity is at risk
Indicates activity is behind schedule and critical
ID | Task | Task Lead | Start Date | End Date | Actual End Date | % Complete | Project Status | Meeting Comments/ Notes & Progress Updates | Updates from Core Team (As of XXX Date)
Goal #1 - Development of Youth Group
Strategy #1: Selection of Members | [5 empty] | 100%
1.1.1 | Determine mandated positions from AB472 | Governor's Office |  |  |  | 100%
1.1.2 | Governor appoints members | Governor's Office |  |  |  | 100%
1.1.3 | Ensure youth member positions are always filled | JJOC and Governor's Office |  |  |  | 100%
Strategy #2: Process for Continued Participation | [5 empty] | 10%
1.2.1 | Develop strategy to incentivize youth participation | Sub Committee |  |  |  | 10% |  | Ice Breaker Meeting | No meeting held in March. Will updated after 4/11/18 meeting.
1.2.2 | Determine budgetary needs if a stipend is offered | JJOC |  |  |  | 10% |  | Potential gas cards
Goal #2 - Communication of Youth Voice
Strategy #1: Determine Areas to Address from Youth Perspective | [5 empty] | 35%
2.1.1 | Select sites to visit | Sub Committee |  |  | ongoing | 100% |  | Reviewed locations
2.1.2 | Schedule site visits | Sub Committee |  |  | ongoing | 75% |  | Murphy Bernadini site visit 3/9/18; Jan Evans visit on 9/11/18 | Next site visits 11.13.18 and 11.14.18 at Caliente, Summit View and CCDC
2.1.3 | Develop youth focused areas for focus | Sub Committee |  |  |  | 0%
2.1.4 | Determine potential intercepts | Sub Committee |  |  |  | 0%
2.1.5 | Determine process how areas of focus can be revised | Sub Committee |  |  |  | 0%
Strategy #2: Determine Communication Format | [5 empty] | 50%
2.2.1 | Develop format to provide feedback to JJOC | Sub Committee |  |  |  | 100%
2.2.2 | Determine if there are other avenues and/or platforms to provide education and communication | Sub Committee |  |  |  | 0% |  | participation in other committees