## PIP Strat Sum & TA Plan
PIP Strategy Summary and TA Plan
State: | Nevada
Date Submitted: | 2013-03-15
Primary Strategies | Key Concerns | TA Resources Needed
Preserve Connections and strengthen relationships | Develop and implement a workforce development plan in consultation with the NRC for caseworkers and supervisors to enhance knowledge and skills for engaging parents in team meetings | Will not be needed
Preserve Connections and strengthen relationships | Evaluate and revise standards in consultation with the NRC that will guide the caseworkers contact with children and parents | Will not be needed
Expand service options and create flexibility for services to meet the needs of children and families | Assess and revise, in consultation with the NRC, if needed, the recruitment plans for foster and adoptive parents by jurisdiction | Rural Region utilized the NRC for the development of recruitment Plans for the QTR 5 PIP submission.

## A. PIP matrix
IV. PIP Matrix
State: | Nevada
Date Submitted: | 2013-03-15
PIP:
Quarterly Report: | X
Quarter: | Q 9
Part A: Strategy Measurement Plan and Quarterly Status Report
Primary Strategy: 1 COMPLETED | Strengthen and reinforce safety practices throughout the life of the case |  |  | Applicable CFSR Outcomes or Systemic Factors: | Safety Outcome 1 and 2
Goal: 1 COMPLETED | Continue the development of Nevada’s safety assessment model to include assessment of children in out-of-home care and at specific milestones throughout the life of the case |  |  | Applicable CFSR Items: | 2, 4
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
1.1.1 Prepare a statewide work plan including unique jurisdictional needs in consultation with an NRC or other T/TA and agency representatives to develop the policies and tools and transfer of learning that support the assessment of safety throughout the life of the case | DCFS, WCDSS, CCDFS Directors/designee | Copy of State work plan (including each jurisdiction) | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1 - attached copy of State Plan named "Nevada's Child Welfare Safety Models" with cover sheet labeled Quarter 1 PIP 1.1.1 Clark, Washoe, Rural. Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 1.1.1 achieved per RO IX (JR).
1.1.1 (A) Develop or refine policies and tools that meet the individual jurisdictional needs pursuant to the work plan to support safety assessments throughout the life of the case and prepare a written safety practice overview to document and articulate Nevada’s safety model | DCFS, WCDSS, CCDFS Directors/designee | Copy of policies and tools | Q 4 | Q4 (1/26/12) RO IX (WE) | Q4-attached with seperate cover sheets labeled Quarter 4 PIP 1.1.1(A) Clark, Quarter 4 PIP 1.1.1(A) Washoe and Quarter 4 PIP 1.1.1(A) Rural. Q4--RO received documents and benchmark completed. RO IX (WE) 01/26/12
1.1.2 Convene a group of agency supervisors and managers to develop supervisory consultation guides and tools to support supervisory oversight of the safety assessment throughout the life of the case | DCFS, WCDSS, CCDFS Directors/designee | Safety guides and tools for supervisors | Q 4 | Q4 (1/26/12) RO IX (WE) | Q4-attached with seperate cover sheets labeled Quarter 4 PIP 1.1.2 Clark, Quarter 4 PIP 1.1.2 Washoe and Quarter 4 PIP 1.1.2 Rural. Q4--RO received documents and benchmark completed. RO IX (WE) 01/26/12
1.1.3 Develop a training plan for the completion of the safety training for staff development on implementation of the safety assessment model including: Safety Plan Development; Linking case plan activities to identified service needs to address safety concerns; developing staff experts and mentors; develop supervisory knowledge and skills in safety consultations; and provide stakeholder orientation on Nevada’s safety assessment model | DCFS, WCDSS, CCDFS Directors/designee | Copy of plan | Q 5 | Q5 (04/01/12) RO IX (WE) | Q5- attached with separate cover sheets labeled Quarter 5 PIP 1.1.3 Clark, Quarter 5 PIP 1.1.3 Washoe and Quarter 5 PIP 1.1.3 Rural. RO received copy of plan. Benchmark completed. RO IX (WE) 04/01/12
1.1.3 (A) Deliver one safety assessment training in Clark County first following by Washoe and Rural. | CCDFS, WCDSS, DCFS | Agenda and Training | Clark: Q5 Washoe Q6 Rural Q7 | CLARK: Q5 (04/01/12) RO IX (WE) WASHOE: Q6 (7/30/12) RO IX (WE) RURAL: Q7 (9/28/12) RO IX (WE) | Q5- attached with separate cover sheets labeled Quarter 5 PIP 1.1.3 (A) Clark. RO received documents to support training delivered in Clark. Benchmark completed. RO IX (WE) 04/01/12. Q6- attached with separate cover sheet labeled Quarter 6 PIP 1.1.3 (A) Washoe. RO received documents supporting completion of safety training in Washoe. RO IX (WE) 07/31/12 Q7: RO received supporting documentation. Benchmark completed. RO IX (WE) 9/28/12
Renegotiated Action Steps and Benchmarks
Primary Strategy: 1 | Strengthen and reinforce safety practices throughout the life of the case |  |  | Applicable CFSR Outcomes or Systemic Factors: | Safety Outcome 1 and 2, Permanency Outcome 2
Goal: 2 COMPLETED | Reduce the number of short term emergency removals under circumstances that do not involve a child abuse neglect allegation |  |  | Applicable CFSR Items: | 1, 3, 15
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
1.2.1 Conduct an analysis of reports on emergency removals due to parental incarceration to determine the circumstances, including time of day and day of the week | DCFS, WCDSS, CCDFS Directors/Designee | Written Summary | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1- Written Summary of analysis provided from the three jurisdictions named as follows: Clark Parental Incarceration Report, WCDSS Parental Incarceration Report and Rural Parental Incarceration Report with cover sheets labeled Quarter 1 PIP 1.2.1 for Clark,Washoe, Rural. Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 1.2.1 achieved per RO IX (JR).
1.2.1 (A) The State in collaboration with the jurisdictions will present the results to local stakeholders to develop an action plan in response to the outcome of the analysis | DCFS, WCDSS, CCDFS Directors/Designee | Action Plan by jurisdiction | Q 2 | Q2 (6/30/11) per RO IX | Q 2- Written Emergency Removal Action Plan provided from the three jurisdictions named as follows: Clark County Action Plan for Emergency Removals, Division of Child and Family Services Rural Region Response, Washoe County Action Plan-Incarcerated Parents with cover sheets labeled Quarter 2 PIP 1.2.1(a) for Clark, Rural and Washoe.
1.2.2 Rural DCFS will implement a pilot project of facilitated family meetings in an identified District for all emergency removals to identify alternative actions | DCFS Rural Region Manager | Documents from team meetings | Q 3 | Q3 (9/30/11) per RO IX | Q 3-PIP- item labeled "Facilitated Family Meetings Pilot Project For Rural Nevada" with PIP Item 1.2.2 as heading. Q3: RO confirms pilot has begun and will continue, despite significant staff turnover. They are prepared to analyze results upon completion. Amount of meetings will vary and depend upon specific removals in jurisdiction.
1.2.3 Washoe and Clark will explore expanding current relative search capacity to conduct relative searches 24/7 and will provide DCFS an informational report on the outcome | DCFS, WCDSS, CCDFS Directors/Designee | Copy of informational report | Q 3 | Q3 (9/30/11) per RO IX | Q 3-PIP- Copy of Information report from Clark and Washoe. Clark's report is labeled "Clark County CFSR Pogram Performance Improvement Quarter 3 Report' and Washoe's report is in the from of a letter from Washoe County's Director dated 9/1/2011 with subject line : PIP item 1.2.3. Q3 RO has reviewed and accepted documentation. Washoe determines expansion not feasible due to budget constraints at this time. Clark operating 24/7 searches currently.
Renegotiated Action Steps and Benchmarks
Primary Strategy: 2 | Preserve connections and strengthen relationships |  |  | Applicable CFSR Outcomes or Systemic Factors: | Permanency Outcome 2, Case Review System
Goal: 1 COMPLETED | Enhance the capacity of child welfare staff to effectively engage children, youth and families in case decision making |  |  | Applicable CFSR Items: | 14, 25
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
2.1.1 Training Management Team (TMT) will conduct a review of best practices and develop guidelines for engaging parents in team meetings | TMT | Copy of guidelines | Q 3 | Q3 (9/30/11) per RO IX | Q 3-Copy of Guidelines labled "Nevada Partnership for Training-Nevada Program Improvement Plan Response to 2.1.1 Review of best practives and develop guidelines for engaging parents in team meetings". Q3 RO has reviewed documentation. The State has completed this benchmark and comleted a literature review and developed guidelines for engagement.
2.1.2 Develop and implement a workforce development plan in consultation with the NRC for caseworkers and supervisors to enhance knowledge and skills for engaging parents in team meetings; initiating in Clark County first | DCFS, WCDSS, CCDFS Directors/Designee | Copy of training plan and parent survey | Clark: Q6 Rural: Q7 Washoe: Q8 | Q6 Clark, Washoe and Rural Completed WE RO IX 7/30/12 | Q6- attached with separate cover sheet labeled Quarter 6 PIP 2.1.2Clark. Also received documentation for Washoe and Rural. Q6 RO IX Copy of training plan and parent survey received. (WE) 7/30/12
Renegotiated Action Steps and Benchmarks
Primary Strategy: 2 | Preserve connections and strengthen relationships |  |  | Applicable CFSR Outcomes or Systemic Factors: | Permanency Outcome 2
Goal: 2 COMPLETED | Create a child welfare agency culture that values and supports the development of relationships between caseworkers and family members, and recognizes the behavioral change process |  |  | Applicable CFSR Items: | 13,16
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
2.2.1 Child Welfare leaders in Nevada will develop and disseminate an initiative statement supporting family centered practice | DCFS, WCDSS, CCDFS Administrators | Copy of initiative statement | Q 2 | Q2 (6/30/11) per RO IX | Q 2- Written Statement on DCFS letterhead titled Nevada's Initiative Statement for Family Centered Practice with cover sheet labled Quarter 2 PIP 2.2.1.
2.2.1 (A) Present the initiative statement to state and local stakeholders for support and commitment | DCFS, WCDSS, CCDFS Directors/Designee | Dissemination Plan | Q 3 | Q3 (9/30/11) per RO IX | Q 3-Dissemination Plan labled PIP item 2.2.1 (A) Initiative Statement Dissemination Plan with attachements included. Q3 RO has reviewed documentation. State has created internal marketing program/branding with their initiative statement that external partners will observe at meetings, conferences, visits to their offices.
2.2.1 (B) Evaluate and update the existing training, both CORE and ongoing to ensure consistency with the initiative statement | DCFS, WCDSS, CCDFS Directors/Designee | Revised Training curriculum | Q 4 | Q4 (1/26/12) as per RO IX (WE) | Q4-attached with cover sheet labeled Quarter 4 PIP 2.2.1 (B). RO received documents and benchmark completed. RO IX (WE) 01/26/12
Renegotiated Action Steps and Benchmarks
Primary Strategy: 2 | Preserve connections and strengthen relationships |  |  | Applicable CFSR Outcomes or Systemic Factors: | Well-Being Outcome 1
Goal: 3 Completed | Improve the quality of caseworker contacts with children and parents |  |  | Applicable CFSR Items: | 18, 19, 20
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
2.3.1 Evaluate and revise standards in consultation with the NRC that will guide the caseworker’s contact with children and parents | DCFS, WCDSS, CCDFS Directors/ designee | Copy of the enhanced contact guidelines | Q 2 | Completed Q2 (6/30/11) per RO IX | Q 2- Written Standards for Caseworker contacts with Children and Parents from the three jurisdictions named as follows: Clark County Standards for Caseworker Contacts with Children and Parents, State of Nevada Division of Child and Family Services (DCFS) PIP item 2.3.1.,Washoe County Department of Social Servicies PIP item 2.3.1. with cover sheets labeled Quarter 2 PIP 2.3.1 for Clark, Rural and Washoe.
2.3.1 (A) Provide caseworkers and supervisors with training and support in the application of the child and parent contact standards to enhance the level of caseworker engagement; initiating in Clark County first | DCFS, WCDSS, CCDFS Directors/ designee | Copy of training outline | Clark: Q 4 Washoe and Rural: Q5 | CLARK: Q4 (1/26/12) RO IX (WE). WASHOE AND RURAL: Q5 (04/01/12) RO IX (WE). | Q4-attached with seperate cover sheet labeled Quarter 4 PIP 2.3.1(A) Clark. Per Clark: RO received documents and benchmark completed. Per Washoe: discussion regarding PII study. For Q5, Washoe to submit documentation indicating training of random sample of staff, roughly 18 of 43 and then research requires study of those trained prior to rolling out further training. RO has agreed to accept the pilot training. RO IX (WE) 01/26/12. Q5-attached with seperate cover sheet labeled Quarter 5 PIP 2.3.1(A) Washoe and Quarter 5 PIP 2.3.1(A) Rural. Q5: RO received copy of training outlines for Washoe and Rural. RO IX (04/01/12) WE
2.3.1 (B) DCFS will review a sample of case documentation of child and parent contacts to evaluate the impact and usage of the contact standards | DCFS | Report of case documentation | Q 7 | Completed Q7 RO IX (WE) | Report of case documentation received. RO IX (9/29/12) WE
2.3.1 (C) Each jurisdiction will implement a peer or supervisory review to evaluate the quality of contacts | DCFS, WCDSS, CCDFS Directors/ designee | Description of the peer or supervisory review by jurisdiction | Q 8 | Completed Q8 RO IX WE | Q8- attached with separate cover sheets labeled Quarter 8 PIP 2.3.1 (C) Clark, Quarter 8 PIP 2.3.1 (C) Washoe and Quarter 8 PIP 2.3.1 (C) Rural. Q8: RO IX received documentation (12/30/12) WE
Renegotiated Action Steps and Benchmarks
Primary Strategy: 3 COMPLETED | Improve the Timeliness and Appropriateness of Permanency Planning across the Life of the Case |  |  | Applicable CFSR Outcomes or Systemic Factors: | Permanency Outcome 1, Termination of Parental Rights, Notice of Hearings and Reviews to Caregivers
Goal: 1 COMPLETED | Reduce the number of children in out of home care for 18 months or longer and reduce barriers to adoption and TPR |  |  | Applicable CFSR Items: | 7, 8, 9, 10, 28, 29
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
3.1.1 Collaborate to assess major barriers within the courts and the agencies to achieve timely adoption | CIP Coordinator; DCFS, WCDSS, CCDFS Directors/Designee | Report of identified barriers | Q 1: 3/23/11 due date moved from Q1 to Q2 as per RO IX | Q2 (6/30/11) per RO IX | Q 1 - Per discussion with Jewel Roberts, ACF, Child Welfare Program Specialist on 3/23/2011 this item (3.1.1) has been moved to a due date of Q 2 since this item could not be completed until completion of items 3.1.2, and 3.1.2 (B) which are Q 2 items. Q1 - agreed to move benchmark (3.1.1) due date to Q2 per conversation with NV DCFS on 3/23/11 per RO IX (JR). Q 2-Written Report of identified barriers and Action Plan named Nevada's Community Improvment Councils' Action Plans Nevada Court Improvment Program Select Committee with cover sheet labled Quarter 2 PIP 3.1.1, PIP 3.1.2(C).
3.1.2 Convene a workgroup by jurisdiction (60-90 days), led by judges (including stakeholders/partners, GAL’s, DA’s) and includes a cross representative from another jurisdiction to share experiences and understand lessons learned to improve functioning and efficiency of adoption/TPR process | AOC, DCFS, WCDSS, CCDFS Directors/Designee | List of Members by jurisdiction | Q 2 | Q2 (6/30/11) per RO IX | Q 2- Written List of Workgroup members by jurisdictions named PIP 3.1.2 List of Members Community Improvement Council (CIC) with cover sheets labeled Quarter 2 PIP 3.1.2 for Statewide Membership across all jurisdictions.
3.1.2(A) CIP/Courts and jurisdictions will develop baseline data on TPR/Adoption to inform workgroups | DCFS, AOC, WCDSS, CCDFS | Baseline data | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1 - attached CIP/Courts and jurisdictional data reports named " Judicial District Community Improvement Council" Data Profile for each Judicial District with cover sheet labeled Quarter 1 PIP 3.1.2(a). Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 3.1.2 (a) achieved per RO IX (JR).
3.1.2 (B) CIP will develop and disseminate a letter including a checklist, timeframes and expectations of the charge of the workgroup | AOC | Letter | Q 2 | Q-1 (3/31/11) per RO IX (JR) | Q 1 - attached letters on letterhead from the Supreme Court of Nevada Administrative Office with cover sheet labeled Quarter 2 PIP 3.1.2(b). Q1 - referenced documents received by RO on 3/31/11. completed a qtr earlier than targeted...kudos, NV! Document review completed by RO IX on 4/22/11. Benchmark 3.1.2(b) achieved per RO IX (JR).
3.1.2 (C) Identify barriers and develop a plan to address barriers within 120 days | DCFS, AOC, WCDSS, CCDFS | Plan | Q 4 | Q2 (6/30/11) per RO IX | Q 2 for Q 4-this is being submitted early during Q 2. Written Report of identified barriers and Action Plan named Nevada's Community Improvment Councils' Action Plans Nevada Court Improvment Program Select Committee with cover sheet labled Quarter 2 PIP 3.1.1, PIP 3.1.2(C).
3.1.3 Each jurisdiction will convene a team to review a sample of cases that have been in out of home for more than 18 months and have a low prognosis of achieving permanency within the next 12 months | Clark, Washoe & Rural Directors/ designee | Reports of reviews | Q 4 | Q4 (1/26/12) RO IX (WE) | Q4-attached with seperate cover sheets labeled Quarter 4 PIP 3.1.3 Clark, Quarter 4 PIP 3.1.3 Washoe and Quarter 4 PIP 3.1.3 Rural. RO received documents and benchmark completed. RO IX (WE) 01/26/12
3.1.3. (A) Based upon the review of cases, agencies will develop a plan to expedite permanency plans and institute process changes to reduce future and ongoing barriers to permanency | Clark, Washoe & Rural Directors/ designee | Copy of plans for expedited permanency | Q 5 | Q5 (04/01/12) RO IX (WE) | Q5- attached with separate cover sheets labeled Quarter 5 PIP 3.1.3 (A) Clark, Quarter 5 PIP 3.1.3 (A) Washoe and Quarter 5 PIP 3.1.3 (A) Rural Q5: RO received copies of expedited plans for each jurisdiction. RO IX (04/01/12) WE.
Renegotiated Action Steps and Benchmarks
Primary Strategy: 4 COMPLETED | Strengthen Child welfare Supervision and middle management skills |  |  | Applicable CFSR Outcomes or Systemic Factors: | Permanency Outcome 1, Initial Staff Training, On-going Staff Training
Goal: 1 COMPLETED | Strengthen supervisory consultation practices and skills at key decision points improving permanency |  |  | Applicable CFSR Items: | 6, 32, 33
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
4.1.1 Identify timeliness to permanency management reports | Statewide data team will work with the DMG | List of management reports | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1- Attached list named PIP 4.1.1-"PERMANCEY REPORTS" with cover sheet labeled Quarter 1 PIP 4.1.4. Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 4.1.1 achieved per RO IX (JR).
4.1.1 (A) Develop data reports that have been identified to measure timeliness to permanency | DCFS, WCDSS, CCDFS Directors/designee | Reports | Q3: Renegotiated to Q4. Q 4: Negotiated to Q7 | Q7 Completed RO IX (WE) | Q3: Negotiated to Q5 due to need for collaboration with other agencies that have pending priorities outside of child welfare. RO 9/30/11. Q4: Renegotiated to Q7 to align with 4.1.2 and to ensure accurate data input in the Chapin Hall database. Q7: Documentation received. Benchmark completed RO IX (WE) 9/28/12
4.1.2 Develop and format supervisory and management tools, guidance and expectations regarding data reports to monitor and improve performance on permanency outcomes | DCFS, WCDSS, CCDFS Directors/designee | Supervisory and management tools reflecting guidance and expectations | Q 4: Negotiated to Q7 | Q7 Completed RO IX (WE) | Q3: Negotiated to Q5 due to need for collaboration with other agencies that have pending priorities outside of child welfare. RO 9/30/11 Q4: Renegotiated to Q7: Chapin Hall is working with the Agency to correct data to ensure accuracy of reports. Converting UNITY data to viable use by Chapin Hall has been problematic. Creating data reports simply to create reports doesn't appear to be an effective use of Agency time. Moving this deliverable to Q7 will allow Agency to spend time with the Chapin Hall data concerns rather than diverting energy to creating reports that will no longer be used once Chapin Hall database is up and running. RO IX (WE) 01/26/12 Documentation received RO IX (WE) 9/28/12
4.1.3 Identify effective supervisory/manager training and development programs | DCFS, WCDSS, CCDFS Directors/designee | Report on training programs | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1- attached report named " I. Marsha Salus Supervisory training and II. Marsha Salus Manager Training" with additional documents from Clark named " Child Protection Supervisory Expectations", " In-Home Supervisory Expectations" , "Receiving Supervisory Expectation, Planned Placement Supervisory Expectations, Caregiver Support Supervisory Expectations, Permanency Supervisory Expectations, Adoption Supervisory Expectations, and ICPC Supervisory Expectations with a cover sheet labeled Quarter 1 PIP 4.1.3 Clark, Washoe, Rural. Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 4.1.3 achieved per RO IX (JR).
4.1.4 Adopt a supervisor/manager training curriculum | DCFS, WCDSS, CCDFS Directors/designee | Copy of curriculum | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1- attached copy of Marsha Salus Curriculum named " Effective Leadership Making the Transition from Family Services Specialist to Supervisor" with cover sheet labeled Quarter 1 PIP 4.1.4. Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 4.1.4 achieved per RO IX (JR).
4.1.4. (A) Conduct initial supervisor/manager training with potential train the trainer candidates | DCFS, WCDSS, CCDFS Directors/designee | Training records | Q 1 | Q-1 (3/31/11) per RO IX (JR) | Q 1-attached copy of training records not named with cover sheet labeled Quarter 1 PIP 4.1.4 (a) Clark and Quarter 1 PIP 4.1.1(a) Rural Washoe. Q1 - referenced documents received by RO on 3/31/11. Document review completed by RO IX on 4/22/11. Benchmark 4.1.4(a) achieved per RO IX (JR).
4.1.4 (B) Develop Nevada based trainers that can be certified to deliver the training for child welfare supervisors/managers across the state | DCFS, WCDSS, CCDFS Directors/designee | List of trainers certified | Q 5 | Q5 (04/01/12) RO IX (WE) | Q 5-attached copy of list of statewide trainers with cover sheet labeled Quarter 5 PIP 4.1.4 (B). Q5: RO received list of certified trainers. (04/01/12) WE
Renegotiated Action Steps and Benchmarks
Primary Strategy: 5 COMPLETED | Expand Service options and create flexibility for services to meet the needs of children and families. |  |  | Applicable CFSR Outcomes or Systemic Factors: | Well-Being Outcome 1, 3, Statewide Information System, Service Accessibility, Individualizing Services, Coordination of CFSP Services with Other Federal, Programs, Diligent Recruitment of Foster and Adoptive Homes
Goal: 1 COMPLETED | Enhance independent living services for children age 15 and older and strengthen foster parent skills and supports |  |  | Applicable CFSR Items: | 17, 22, 23, 24, 36, 37, 40, 44
Action Steps and Benchmarks | Person Responsible | Evidence of Completion | Quarter Due | Quarter Completed | Quarterly Update
5.1.1 Develop a policy/procedure re: transition goals addressing necessary domains (education, housing, medical, mental health) for youth with OPPLA goals | DCFS, WCDSS, CCDFS Directors/designee | Policy and procedure | Q 2 | Q2 (6/30/11) per RO IX | Q 2 Policy and Procedure developed and approved by DMG on 12/17/10 named policy 0801 Youth Independent Living Program with cover sheet labled Quarter 2 PIP 5.1.1.
5.1.2 Assess and identify UNITY capability for tracking transition plans and youth outcomes | DCFS, WCDSS, CCDFS Directors/designee | UNITY reports | Q 3 | Q3 (9/30/11) per RO IX | Q 3- Unity Report labled "IL 90 Day Report (CFS7L9)" included as attachment "2" with document labled "PIP item 5.1.2 " and attachments 1 and 2. Q3 RO has reviewed documentation. State has assessed, identified and created reports.
5.1.3 Collaborate with CIP select committee, youth and community stakeholders to focus on improving youth transition, including youth participation in court and develop a plan | DCFS, WCDSS, CCDFS Directors/designee | Recommendations | Q 3 | Q3 (9/30/11) per RO IX | Q 3-Recommendations labled PIP item 5.1.3" with attachements 1-9. Q3 RO has reviewed and accepted the documentation. The State has not only collaborated with CIP, youth and stakeholders, but also passed a FC bill of rights and held a statewide conference and provided information to judges, updated/created benchcards for judges and amend IL policies on an ongoing basis.
5.1.4 Convene a workgroup to collaborate with the provider agencies regarding training for foster parents on behavioral issues | DCFS, WCDSS, CCDFS Directors/designee | Plan | Q 3 | Q3 (9/30/11) per RO IX | Q 3-Plan labled PIP 5.1.4. Q3 The RO has received the documentation. The plan has been developed.
5.1.4 (A) Develop a standardized curriculum for emotional/behavioral issues and behavioral management for specialized foster care parents to increase their knowledge of emotional and behavioral characteristics demonstrated by children in foster care and the impact of multiple placements | DCFS, WCDSS, CCDFS Directors/designee and provider agencies | Revised curriculum | Q 6 | Q6 Completed RO IX WE 7/30/12 | Q6- attached with separate cover sheets labeled Quarter 6 PIP 5.1.4(A) Statewide. Revised curriculum received. RO IX WE 7/30/12
5.1.4 (B) Evaluate contracts and require standardized curriculum | DCFS, WCDSS, CCDFS Directors/designee and Fiscal staff | Contracts | Q 6 | Q6 Completed RO IX WE 7/30/12 | Q5- attached with separate cover sheets labeled Quarter 6 PIP 5.1.4(B) Statewide RO IX WE Documentation received. Completed 07/30/12
5.1.5 Identify foster parent champions and disseminate contact information to foster parents | DCFS, WCDSS, CCDFS Directors/designee | Disseminated information | Q 4 Renegotiated to Q6 | Rural Completed. RO IX (WE) 01/26/12 Clark and Washoe completed RO IX WE 7/30/12 | Q4: RURAL: RO received documents and benchmark completed. RO IX (WE) 01/26/12 Washoe and Clark remail pending. Renegotiated benchmark to Q6 for both Washoe and Clark. Due to Clark's size finding enough foster parent champions to cover the area has been problematic. Clark will also problem solve the systemic piece about needing to find a way to update their list to ensure it's viable through time. Washoe pairs a trainer with a foster parent, who is the champion. They will determine the availabililty of the champion 24/7 and ongoing. RO IX (WE) 01/26/12.Q6- attached with separate cover sheets labeled Quarter 6 PIP 5.1.5 Clark and PIP 5.1.5 Washoe RO IX WE Completed 7/30/12
5.1.6 Assess and revise, in consultation with the NRC, if needed, the recruitment plans for foster and adoptive parents by jurisdiction | DCFS, WCDSS, CCDFS Directors/designee | Revised Plans by jurisdiction | Q 5 | Q5 (04/01/12) RO IX (WE) | Q 5-attached copy of recruitment plans for foster and adoptive parents from Clark, Washoe and the Rural Region labled Quarter 5 PIP 5.1.6 Clark, Quarter 5 PIP 5.1.5 Washoe and Quarter 5 PIP 5.1.5 Rural Q5: RO received plans per jurisdiction. RO IX (04/01/12) WE
5.1.7 Negotiate an interagency agreement with the agencies within the Department of Health and Human Services to enable children, youth and families to access services on a priority basis within the limits of state and federal law | DCFS, WCDSS, CCDFS Directors/designee and the DCFS Grants management unit | Copy of agreement | Q 7 | Q7 Completed RO IX (WE) | Q7 Copy of agreement received. RO IX (WE) 9/28/12
Renegotiated Action Steps and Benchmarks

## Part B
State: | Nevada
Date Submitted | 2013-03-15
PIP:
Quarterly Report: | X
Quarter: | Q9
Part B: National Standards Measurement Plan and Quarterly Status Report
Safety Outcome 1: Absence of Recurrence of Maltreatment
National Standard | 94.6%
Performance as Measured in Final Report/Source Data Period | 93.6 for FFY 2007b/2008a
Performance as Measured at Baseline/Source Data Period | N/A
Negotiated Improvement Goal | Met the National Standard in FFY 2008 (95.1%)
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab
| 93.7 | 93.7 | 93.7 | 93.7 | 93.7 | 93.7 | 93.7 | 93.7
Note FY 2010 resulted in 94.5
Safety Outcome 2: Absence of Maltreatment of Children in Foster Care
National Standard | Q1: 99.68%
Performance as Measured in Final Report/Source Data Period | Q1: 99.61 for FFY 2007b/2008a
Performance as Measured at Baseline/Source Data Period | Q1: 99.54 FFY 2009
Negotiated Improvement Goal | Q1: 99.64%
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011
| 99.43 | 99.43 | 99.43 | 99.43 | 99.43 | 99.43 | 99.43
Note: FFY 2010 resulted in 99.40
Permanency Outcome 1: Timeliness and Permanency of Reunification
National Standard | Q1: 122.6%
Performance as Measured in Final Report/Source Data Period | Q1: 153.0 for FFY 2007b/2008a
Performance as Measured at Baseline/Source Data Period | Q1: N/A
Negotiated Improvement Goal | Q1: Met the National Standard at the time of the CFSR Statewide Assessment and Final Report
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY2012 ab
| 134.3 | 134.3 | 134.3 | 134.3 | 134.3 | 134.3 | 134.3 | 134.3 | 126.9
Note FFY 2009 resulted in 136 and FFY 2012 resulted in 134.4
Permanency Outcome 2: Timeliness of Adoptions
National Standard | Q1: 106.4%
Performance as Measured in Final Report/Source Data Period | Q1: 83.1 for FFY 2007b/2008a
Performance as Measured at Baseline/Source Data Period | Q1: 79.5 for FFY 2008
Negotiated Improvement Goal | Q1: 82.8 - Met Miminal improvement achieved FFY 2008b/2009a (85.6)
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2012ab
| 114.5 | 114.5 | 114.5 | 114.5 | 114.5 | 114.5 | 114.5 | 114.5 | 134.8
Note FFY 2009 resulted in 86.3 and FFY 2010 resulted in 108.9
Permanency Outcome 3: Achieving Permanency for Children in Foster Care for Long Periods of Time
National Standard | Q1: 121.7%
Performance as Measured in Final Report/Source Data Period | Q1: 120.3 for FFY 2007a/2008b
Performance as Measured at Baseline/Source Data Period | Q1: N/A
Negotiated Improvement Goal | Q1: Met National Standard achieved FFY 2008 (127.9)
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2012ab
| 144.9 | 144.9 | 144.9 | 144.9 | 144.9 | 144.9 | 144.9 | 144.9 | 139.7
Note FFY 2009 resulted in 135.1 and FFY 2010 resulted in 141.6
Permanency Outcome 4: Placement Stability
National Standard | Q1: 101.5%
Performance as Measured in Final Report/Source Data Period | Q1: 83.1 for FFY 2007b/2008a
Performance as Measured at Baseline/Source Data Period | Q1: 83.1-2007b/2008a
Negotiated Improvement Goal | Q1: 85.6 - Met minimal improvement achieved in FFY 2008b/2009a (86.9)
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2011ab | FFY 2012ab
| 91.4 | 91.4 | 91.4 | 91.4 | 91.4 | 91.4 | 91.4 | 91.4 | 90.5
Note FFY 2009 resulted in 90.1 and FFY 2012 resulted in 93.3

## Part C
State: | Nevada
Date Submitted | 2013-03-15
PIP:
Quarterly Report: | X
Quarter: | Q9
Part C: Item-Specific and Quantitative Measurement Plan and Quarterly Status Report
Outcome/Systemic Factor: ____ Item: ____ | S1 | Item: 1
Performance as Measured in Final Report | 86%
Performance as Measured at Baseline/Source Data Period | The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 80.4
Method of Measuring Improvement | Nevada item measures will be based on targeted case reviews using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 1 is 29. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case review sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 1 is 29. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29 | 2012-05-31 | 2012-08-31 | 2012-11-30
| pending | pending | pending | pending | 79.1 | 76.2 | 76.7 | 81.0 MET
Note: The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: S2; Q2: Item: 3
Performance as Measured in Final Report | Q1: 78%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete.. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3 and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 74.9
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 3 is 41. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 3 is 41. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29
| pending | pending | pending | pending | 76.1MET
Note The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: S2; Q2: Item:; Q3: 4
Performance as Measured in Final Report | Q1: 55%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline. Baseline is not yet established. This will occur January 2011 - December 2011
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 52.5
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 4 is 62. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 4 is 62. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29
| pending | pending | pending | pending | 54.8 MET
Note The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: P1; Q2: Item: 7
Performance as Measured in Final Report | Q1: 63%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 62
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 7 is 40. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 7 is 40. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29 | 2012-05-31 | 2012-08-31 | 2012-11-30 | 2013-03-15
| pending | pending | pending | pending | 57.1 | 59.5 | 59.5 | 61.9 | 69.0
Note The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: P1; Q2: Item:10
Performance as Measured in Final Report | Q1: 43%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 61.3
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 10 is 7. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal cases required to be reviewed for item 10 is 7. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29
| pending | pending | pending | pending | 62.5 MET
Note The baseline period for case reviews will be completed in December 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: WB1; Q2: Item: 17
Performance as Measured in Final Report | Q1: 37%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 46
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 17 is 62. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 17 is 62. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29
| pending | pending | pending | pending | 46.8 MET
Note The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: WB1; Q2: Item: 18
Performance as Measured in Final Report | Q1: 44%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 48.2
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 18 is 57. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 18 is 57. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29
| pending | pending | pending | pending | 54.2MET
Note The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: WB1; Q2: Item: 19
Performance as Measured in Final Report | Q1: 55%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 60.5
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 19 is 62. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 19 is 62. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met.
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29 | 2012-05-31 | 2012-09-28
| pending | pending | pending | pending | 54.8 | 59.7 | 71.0 Met
Note The baseline period for case reviews will be completed in November 2011.
Outcome/Systemic Factor: ____ Item: ____ | Q1: WB1; Q2: Item: 20
Performance as Measured in Final Report | Q1: 44%
Performance as Measured at Baseline/Source Data Period | Q1: The Prospective baseline will be developed using data from January 2011-December 2011. The baseline will be reported in first quarterly status report after the December 2011 reviews are complete. Minimum of 62 applicable cases for this item in baseline.
Negotiated Improvement Goal | Q1: Improvement goal will be set using Method 2 Prospective Formula from CFSR TB#3, and the overlap adjustment will be applied based on the number of quarters the baseline overlaps the PIP approval. 49.7
Method of Measuring Improvement | Q1: Nevada item measures will be based on a targeted case review using a modified version of the current CFSR case review tool. To establish a baseline, reviewers will review 62 cases during the January 2011 to December 31, 2011 period, and the minimal applicable cases required to be reviewed for item 20 is 50. The period under review will cover the 12 months prior to the date the case is reviewed and the sample will consists of 33% In-Home cases and 67% Foster Care cases. In determination of the performance percentages the numerator is the number of applicable cases in three regional sites in which the indicator was determined a strength for the period. The denominator is the total number of applicable cases reviewed across three regional sites for the period. The baseline period for case reviews will be completed in December 2011. Case review results will be reported within 30 days of the review and rolled up for each review, each site as base data and also aggregated for a statewide percentage. The on-going case reviews sample will consists of 62 cases reviewed annually, and the minimal applicable cases required to be reviewed for item 20 is 50. The sample will consists of 33% in-home and 67% foster care. During the evaluation period Nevada will use rolling quarters of data/findings encompassing 12 months to determine whether the improvement goal has been met. | tat
Renegotiated Improvement Goal
Status (Enter the quarter end date and measurement for the reported quarter in cell below) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
| 2/28/2011 | 2011-05-31 | 2011-08-31 | 11/31/2011 | 2012-02-29 | 2012-05-31 | 2012-08-31 | 11/30.2012
| pending | pending | pending | pending | 49.1 | 42.6 | 45.5 | 50.9 MET
Note The baseline period for case reviews will be completed in November 2011.
Note